## Description
COMP 5700/5703/6700/6706 -- Software Process
Iteration: | 1
Objective: | To gain experience with TDD
Product: | Write software to initialize the playing surface for a strategy game.
Deliverables: | Via Canvas: | Include this spreadsheet with completed process information with your Canvas submission.
| Via GitHub: | Push your code to GitHub Classroom
Notes on Process: | - Follow the process in the "Process" worksheet for this assignment.
- This homework assignment is be accomplished individually
- Ensure you follow the course coding and counting standards.
- Be honest in your data. Your grade depends on how you follow the process and the quality of your work, not on the speed of your work or the number of defects found.
- Below are clarifications for process worksheets that have been problematic in the past:
|  | Worksheet | Special Instructions
|  | Plan | Record lines of code for production code only. Do not include test code.
|  | Acceptance | Develop acceptance tests for the specified black box. Do not include tests for items that are not part of the specifications (meaning, items over and above the specs -- these tests will appear in your individual unit test files). Write the expected results at planning time. Modify if necessary later. Don’t write actual results in advance. Actual results should reflect the state of the software at the time of delivery.
|  | Time Log | Use the "sandbox" activity to record time spent experimenting with the assignment requirements.
|  | Change Log | The "Reference to a Previous Change" column allows you to indicate that you are fixing a fix. The value in the column should be the number on the change log of the fix you are repairing.
|  | Historical Data | Record your process and product data from all previous programming assignments. Do this as part of the planning activity.
|  | Review | During the planning activity, list a count of all defects that you've previously encountered. Construct a checklist from your defect logs. Indicate during the review activity the number of times the review checklist item found an error.
|  | Scenarios | Create an interface specification depicting the interaction between a test driver and the class specified above. Create nominal scenario(s) and anomalous scenario(s) sufficient to convey your understanding of software behavior
|  | Lessons Learned | This tab is optional. Use it to record great ideas, suggestions, etc. Whining is not productive :)
|  | Architecture | Develop CRC cards only for the production code needed to implement the specifications. Do not include CRC cards for test drivers.
|  | Estimate | Record all the items from your architecture. Do not include test code.
|  | Iterations | Record the number of iterations you plan to use, together with the planned velocity of each iteration. Record the amount of time you plan to have available each day of the project window. Please plan for more than one iteration.
Special Instructions: | - Selected cells in this spreadsheet are locked against inadvertent editing. Should you need to unlock the spreadsheet, select the protected worksheet, select Tools -> Protection -> unprotect.

## Process
Constants |  |  |  | 0
Start date: | 36526 |  | Grades: | 1
End date: | 73051 |  |  | 0.95
Phases: | Analyze | Identifying customer needs |  | 0.9
| Architect | High-level design |  | 0.85
| Plan project | Determine actions/effort for project duration |  | 0.8
| Plan iteration | Determine actions/effort this iteration |  | 0.75
| Construct | Low-level design, coding, unit testing |  | 0.7
| Refactor | Restructure internal design |  | 0.65
| Review | Examine test code for risk mitigation |  | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | did not follow
| Requirements Clarification | Clarifications to requirements |  | very painful
| Product syntax | Syntax flaws in the deliverable product |  | painful
| Product logic | Logic flaws in the deliverable product |  | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | very helpful
| Test syntax | Syntax flaws in the test code
| Test logic | Logic flaws in the test code
| Test interface | Flaws in the interface of a component of the test code
| Test checking | Flaws with boundary/type checking within a component of the test code
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 0
Y/N: | Yes |  |  | 0
| No |  |  | 0
Proxy Types: | - |  |  | Base
| Calculation |  |  | New
| Data |  |  | Reusable
I/O
Logic
Sizes: | VS | S | M | VL
upper | -1.5 | -0.5 | 0.5 | 99999
mid | -2 | -1 | 0 | 2
lower | 0 | -1.5 | -0.5 | 1.5
| 0 | 0 | 0
<-- Mandatory |  | ✔
Process Script
Minimal Guiding Indicators |  |  |  | Minimal Sufficient Activities
| Goal | Indicator |  |  | Engineering Activities
| Cost: | None |  |  | Envision
| Schedule: | On time |  |  | Analyze
| Performance: |  |  |  | Synthesize
| Product: |  |  |  | Architecture
| NFR: | None |  |  | Articulate
| FR: | Equivalence Class Partitioning |  |  | Construct
| Process: | Completed spreadsheet |  |  | Interpret
Integration Test
Operational Activities
Plan
Plan project
Monitor/Control
Post Mortem
Release
Minimal Viable Process |  |  |  | Minimal Effective Practices
|  |  |  | MSA | MEP | Spreadsheet tab on which to document MEP
|  |  |  | Pre-project | • Accept invitation to GitHub Classroom
• Pull your GitHub CLassroom repo into your PyDev Eclipse project
• Grad students only: Set up an IBM Cloud microserver
|  |  |  | Plan Project | • Guess projected LOC | Plan
[5 empty] | • Guess projected effort (in minutes) | Plan
|  |  |  | Construction | • Repeat
• • Select/write a test case
[5 empty] | • • Run the test a red light test | Acceptance (if test is an acceptance test)
• • While the test is not red
• • • Diagnose why the test was not red
• • • If the problem was due to incorrect test code
[5 empty] | • • • • Fix the defect and log it in the change log | Change Log
• • • • Run the test as a red light test
• • • Else
• • • • Continue to the next red light test
• • Build enough production code to make the test pass
• • Run the test as a green light test
• • While the test is not green
[5 empty] | • • • Fix the defect and log it in the change log | Change Log
• • • Run the test as a green light test
• • Clean up the code as appropriate and run as blue light
• Until test coverage is sufficient and all tests pass
• Commit all code to git
|  |  |  | Review | • Perform rubber duck review of test code | Change Log
|  |  |  | Refactor | • Refactor production code to remove odious smells; run as blue light | Change Log
|  |  |  | Post Mortem | • Record acceptance test results | Acceptance
[5 empty] | • Count production LOC | Plan
[5 empty] | • Record lessons learned (optional) | Lessons
|  |  |  | Release | • Commit all code to git
• Push to GitHub.com
• Upload spreadsheet to Canvas
Minimal Guiding Indicators |  |  |  | Monitor | • Record time spent in each activity. | Time Log
Cost: |  | - |  |  | • Record defects, changes to requirements. | Change Log
Schedule: |  | Submitted on time
Performance:
Product:
| NFR: | Meets delivery requirements.
| FR: | Boundary Value Analysis
| Process: | Evident on spreadsheet
Operational Engineering
Project Planning
Post Mortem
Release
Monitor/Cntrl
Construct
Not all components are constructed
Analyze
Review
Refactor
Failed review

## Customer Needs
Customer Needs
Background: | We are developing a set of microservices for the strategy board game Othello. Each microservice receives its input as a Python dictionary represented by a URL-encoded query string and outputs its result as UTF-8 string of a Python dictionary.
Functional Specifications: | sudoku
|  | Abstraction: | othello is a backend HTTP microservice that manipulates an Othello board based on parameters passed to it.
| method |  | description
This functionality is provided for you ➜ |  | GET /othello | Performs an operation on an Othello board, where the operation and any accompanying parameters are specified by the query portion of the URL
|  |  | Invocation pattern: | http://name-of-server.com/othello?op=create&size=8
|  |  |  | where | signifies
|  |  |  | name-of-server.com | name of the microservice provider
|  |  |  | othello | name of the microservice
|  |  |  | op | operation to perform ("create," in this particular case)
|  |  |  | size=8 | parameters used in performing the operation ("size," in this particular case)
|  |  | Parameters: | Parameters to the microservice are specified in the query portion of the URL and must be in URL-legal format. All parameters arrive unvalidated. The "op" parameter is mandatory.
|  |  |  | Note: | If names are duplicated in the query string, the leftmost value is associated with the name.
[5 empty] | Example: | ?op=op1&op=op2
results in
"op1" being used as the value of "op"
|  |  |  | Note: | Names in the query string may be designated as empty, in which case they have an empty string as a value. This should not be interpreted as a missing parameter.
[5 empty] | Example: | ?op=op1&parm1=&parm2=
results in
empty strings being used as the values of "parm1" and "parm2"
|  |  | Desired behavior (normal): | Performs the operation named by the 'op' parameter. Returns a string of a Python dictionary containing the results. Operations are:
|  |  |  | Operation Name | Operation Description
|  |  |  | op=create | Creates an initial board
|  |  |  | op=status | Determines the status of the board.
|  |  |  | op=place | Places a token on the board.
|  |  |  | op=next | Automates the next move.
A description of each operation is given in the "operation" section below.
|  |  | Desired behavior (errors): | If: | the query string contains no "op" parameter
|  |  |  | Action: | Return a dictionary element having a key of "status" and a value of "error: xxx", where xxx is a diagnostic string.
|  |  |  | Exit conditions: | No further processing takes place once an error is discovered.
|  |  | State change: | No state is retained by the microservice.
|  |  | General examples: | Valid values
|  |  |  | Input: | http://name-of-server.com/othello?op=create
|  |  |  | Returns: | A string of a dictionary containing the results of the "create" operation
|  |  |  | Input: | http://name-of-server.com/othello?op=create&board=1
|  |  |  | Returns: | A string of a dictionary containing the results of the "create" operation
Invalid values
|  |  |  | Input: | http://name-of-server.com/othello
|  |  |  | Returns: | {'status':'error: no op is specified'}
|  |  |  | Input: | http://name-of-server.com/othello?board=1
|  |  |  | Returns: | {'status':'error: no op is specified'}
|  |  |  | Input: | http://name-of-server.com/othello?op=othello
|  |  |  | Returns: | {'status':'error: op is not a legal operation'}
|  |  |  | Input: | http://name-of-server.com/othello?op=
|  |  |  | Returns: | {'status':'error: no op is specified'}
|  |  | Implementation note: | Server interface code parses the HTTP request query string into a python dictionary and passes the dictionary to _dispatch() which, in turn, calls the component associated with the specified operation. Upon completion, a dictionary containing results is returned to _dispatch() and converted to a string the HTTP response. You should not have to modify microservice.py or dispatch.py. Modules for handling each of the operations have been stubbed and require your modification.
| operation |  | description
Iteration 1 Statement of Work➜ |  | op=create | Creates an initial board.
|  |  | Invocation pattern: | http://name-of-server.com/othello?op=create&light=1&dark=2&blank=0&size=8
|  |  | Relevant dictionary elements: | key | content
|  |  |  | light | light is value that represents the light playing token on the game board. It is a string of an integer in the range [0,9]. Optional, defaulting to '1' if missing. Arrives unvalidated.
|  |  |  | dark | dark is value that represents the dark playing token on the game board. It is a string of an integer in the range [0,9]. Optional, defaulting to '2' if missing. Arrives unvalidated.
|  |  |  | blank | blank is value that represents the an empty position on the game board. It is a string of an integer in the range [0,9]. Optional, defaulting to '0' if missing. Arrives unvalidated.
|  |  |  | size | size describes the number of rows and columns of the game board. It is a string of an even integer in the range [6,16]. Optional, defaulting to '8' if missing. Arrives unvalidated.
Dictionary elements not specified above are ignored.
|  |  | Desired behavior (normal): | Returns a dictionary consisting of the following key-value pairs (see "Support Information" for examples):
|  |  |  | key | content
|  |  |  | board | This key-value pair models the playing surface. The value is a list of integers arranged in row-major order to form a size x size grid. Each value is in the range [0,9]. The board has two light tokens and two dark tokens arranged in the center on a diagonal with each other. The light tokens form a north-west to south-east diagonal and the dark tokens form a north-east to south-west diagonal.
|  |  |  | tokens | This key-value pair is a string of a dictionary that provides values that correspone to light tokens, dark tokens, and empty board positions. The key-values are:
[5 empty] | key | value
[5 empty] | light | The integer value specified by the light parameter
[5 empty] | dark | The integer value specified by the dark parameter
[5 empty] | blank | The integer value specified by the blank parameter
|  |  |  | Integrity | This key-value pair assures the integrity of the playing data. Its value is the sha256 hash hexdigest of the string formed by
concatenating the string value of each of the playing surface cells in column-major order
followed by the string "/<light>/<dark>/<blank>/<next_player>", where
<light> is the value specified by the light parameter
<dark> is the value specified by the dark parameter
<blank> is the value specified by the blank parameter
<next_player> indicates which token should be played next. At creation, <next_player> is the value associated with the dark parameter.
Iteration note: This is an initial integrity check that will be changed in a later iteration.
|  |  |  | status | This key-value pair indicates the status of the game at the time the board is created. The value associated with status at creation time is "ok"
|  |  | Desired behavior (errors): | If: | If any dictionary element violates the description above,
|  |  | In priority order | Action: | Return a dictionary element having only a key of "status" and a value of "error: xxx", where xxx is an appropriate diagnostic string,
|  |  |  | Exit conditions: | And perform no further processing once an error is discovered.
|  |  |  | If: | If the values of light, dark, and blank are not unique,
|  |  |  | Action: | Return a dictionary element having only a key of "status" and a value of "error: xxx", where xxx is an appropriate diagnostic string,
|  |  |  | Exit conditions: | And perform no further processing once an error is discovered.
Future Iteration ➜ |  | op=status | Determines the status of the board.
|  |  | Desired behavior (normal): | Currently stubbed
Future Iteration ➜ |  | op=place | Places a token on the board.
|  |  | Desired behavior (normal): | Currently stubbed
Future Iteration ➜ |  | op=next | Automates the next move.
|  |  | Desired behavior (normal): | Currently stubbed

## Spec Notes (hidden)
Specification Notes

## Support Info
Supporting Information
Our microservice is an implementation of the board game Othello. Rules for the physical game can be found at:
https://en.wikipedia.org/wiki/Reversi
The information below provides implementation guidance.
Starting Board
Upon receipt of the "create" operation, the microservice generates the playing surface and places playing tokens in the appropriate locations. By default,
the board is an 8 x 8 grid
a zero indicates that a position is not occupied by any playing token
a one indicates that a position is occupied by a light playing token
a two indicates that a position is occupied by a dark playing token
These values can be over-ridden by parameters passed through the query segment of the microservice URL.
The board starts with two light tokens and two dark tokens arranged in the center of the board on a diagonal with each other. The light tokens form a north-west to south-east diagonal and the dark tokens form a north-east to south-west diagonal.
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
| 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Input: | http://name-of-server.com/sudoku?op=create&light=1&dark=2&blank=0&size=8
| 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Output: | {
| 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 'board': | [0,0,0,0,0,0,0,0, 0,0,0,0,0,0,0,0, 0,0,0,0,0,0,0,0, 0,0,0,1,2,0,0,0, 0,0,0,2,1,0,0,0, 0,0,0,0,0,0,0,0, 0,0,0,0,0,0,0,0, 0,0,0,0,0,0,0,0],
| 4 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 |  | 'tokens': | {'light': 1,'dark': 2, 'blank': 0},
| 5 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 |  | 'integrity': | 'db24b170e77c8bef5416f5d39e1fb94b82245089416b95305756043dd195fcef',
| 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 'status': | 'ok'
| 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | }
| 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Note: | The value of "integrity" is the sha256 hexdigest of "0000000000000000000000000001200000021000000000000000000000000000/1/2/0/2"
|  | 1 | 2 | 3 | 4 | 5 | 6
| 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Input: | http://name-of-server.com/sudoku?op=create&light=1&dark=2&blank=0&size=6
| 2 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Output: | {
| 3 | 0 | 0 | 1 | 2 | 0 | 0 |  |  |  | 'board': | [0,0,0,0,0,0, 0,0,0,0,0,0, 0,0,1,2,0,0, 0,0,2,1,0,0, 0,0,0,0,0,0, 0,0,0,0,0,0],
| 4 | 0 | 0 | 2 | 1 | 0 | 0 |  |  |  | 'tokens': | {'light': 1,'dark': 2, 'blank': 0},
| 5 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 'integrity': | '6c3ec0129f5e128f48e2541bd6663a52a825c35f99b9a69d9593f2fc44b0bb4b',
| 6 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 'status': | 'ok'
}
[10 empty] | Note: | The value of "integrity" is the sha256 hexdigest of "000000000000001200002100000000000000/1/2/0/2"

## Assessment
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analyze | Identifying customer needs |  | AB | 0.9
| Architect | High-level design |  | B | 0.85
| Plan project | Determine actions/effort for project duration |  | BC | 0.8
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75
| Construct | Low-level design, coding, unit testing |  | CD | 0.7
| Refactor | Restructure internal design |  | D | 0.65
| Review | Examine test code for risk mitigation |  | F | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed | Base
| Calculation |  |  | Not tested | New
| Data |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
<-- Mandatory |  | ✔
Assessment Worksheet
Name: |  | Haden Stuart
User name: |  | has0027
GitHub user name: |  | has0027
URL of microservice: |  |  |  | <-- Grad students only
Instructor Assessment
Product Assessment
Process Assessment:
Score: |  | out of | 100
Grading rubric: Product Aspect
| AA | 100 | Exceptional job worthy of being used as an example of superior work
| A | 95 | Product satisfies all functional requirements, has insignificant nonfunctional requirement nonconformance
| AB | 90 | Product satisfies all functional requirements, has minor nonfunctional requiement nonconformance
| B | 85 | Product satisfies all functional requirements, has major nonfunctional requirement noncomformance
| BC | 80 | Product encounters minor functional deviations, has insignificant nonfunctional requirement nonconfirmance
| C | 75 | Product encounters minor functional deviations, has minor nonfunctional requirement nonconfirmance
| CD | 70 | Product encounters minor functional deviations, has major nonfunctional requirement nonconfirmance
| D | 65 | Product encounters multiple significant problems in functional and nonfunctional requirements
| F | 50 | Deliverables show lack of comprehension of concepts, or are incomplete
Grading rubic: Process Aspect
| AA | 100 | Exceptional job worthy of being used as an example of superior work
| A | 95 | Process has insignificant exceptions
| AB | 90 | Process has multiple minor exceptions
| B | 85 | Process has exceptions that obsure activity verification
| BC | 80 | Process has exceptions with historical data that affect the current project
| C | 75 | Process has exceptions that suggest lack of comprehension of concepts
| CD | 70 | Process has exceptions that bring into question the validity of the data
| D | 65 | Process has exceptions suggesting it wasn't followed.
| F | 50 | Deliverables are incomplete
Quality checks |  |  | changes from the previous assignment are in red
General
Are all regions highlighted in yellow appropriately complete?
Does the workbook reflect a faithful record of information?
Has this assignment been uploaded as specified by the assignment description?
Project Plan Summary
Was the planned information determined before development and not altered after development?
Is planned time expressed in minutes?
Do LOC counts address production code (and exclude test code)?
Is the actual line count calculated according to the counting standard?
Time Recording Log
Does the log reflect a faithful record of time spent?
Do no times span midnight?
Does the log reflect the activities in the specified process?
Is post mortem the final phase?
Does the time recording log reflect the your lifecycle?
Change Log
Is each change accompanied by a description in the "comment" field?
Are changes recorded against the appropriate phase in which they were injected and removed?
Does the "removed" count equal the "injected" count? If not, is the rational documented in the "lessons learned" tab?
Are the dates and times in the change log consistent with the dates and times in the time recording log?
Acceptance Report
Do actual results support expected results?
Do actual results marked as "Passed with issues" include a comment?
Source Code
Does the code reflect the coding standard?
Will the code compile without change?
Does the production code contain any packages that aren't part of the customer's production environment.
Does the code take into consideration specified error conditions?
Does the code fulfill the assignment requirements?
Does the code follow the prescribed directory format (i.e., prod, test, sandbox)?
Historical Data
Is the historical data complete?
Have previously noted problems in process measurements been corrected?
Deliverables
Has the spreadsheet been uploaded to Canvas?
Has all the code been pushed to GitHub?
Is test code in a separate folder?
Will the test code work without modification?
Does the git respository reflect commits at the specified process points?
Does the "Assessment" tab include your name, your AU username, etc.
Review
Did you construct your review checklist during the planning phase?
Does the error count indicated the analysis of defects match your historical defect count?
Are checklist items answerable in "yes" or "no" terms?
Does your checklist reflect at least two common items from your defect log ?
Does your checklist contain more than "mom and apple pie" items?
Refactor
Is code free of the following bad smells: duplicate code, long methods, long classes
temporary variables, useless comments, coding standard violations?
Scenario
Were the scenarios constructed during the analysis phase (and not changed later)?
Does each scenario describe as fully as possible the interaction with the software under construction?
Are the actors correctly identified?
Are suitably understandable examples given?
Are events and responses directly observable?
Architecture
Was the architecture determined before construction (and not changed later)?
Does the architecture reflect a solid initial understanding of the solution?
Does the architecture show all components required for the solution (with the exception of system built-in components)?
Are collaborators specified correctly?
Do functionally-decomposed components have only one operation? Has the operation been given the component name?
Are component operations given names to suggest their behavior?
Does the architecture exhibit "good" design characteristics, such as appropriate levels of coupling, cohesion, etc.?
Estimate
Does each component denoted by a CRC card appear in the estimate as either base code, new components, or reused code?
Is base code vs reuse code identified correctly?
Do the base components and the new comopnents reflect the architecture?
Are the base components and new components sized according to historical proxies?
Is a rationale provided if either the LOCp and/or Ep are overridden?
Does the value of LOCa reflect effort expended on creating, adding, or modifying production code?
Is actual LOC data recorded at post mortem time?
Iterations
Is more than one iteration planned?
Does the WBS list all iterations?
Is the overall estimate of time in the WBS consistent with the calculated effort?
Are the planned completion dates of iterations in the WBS consistent with the calendar?
Are planned times recorded from the start of the calendar through the end of the project?
Does the calendar corroborate the WBS, and visa versa?
Construction
Did you follow the design -> test(failure) -> code -> test(success) -> clean up (if necessary) -> repeat pattern?
Are all unit tests written so that passing the test satisifies requirements?
Are unit tests written to the level of boundary value analysis?
Is there at least one test suite which, when run, exercises the entire production code base?
Does your code pass all test cases?

## Historical Data (hidden)
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analyze | Identifying customer needs |  | AB | 0.9
| Architect | High-level design |  | B | 0.85
| Plan project | Determine actions/effort for project duration |  | BC | 0.8
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75
| Construct | Low-level design, coding, unit testing |  | CD | 0.7
| Refactor | Restructure internal design |  | D | 0.65
| Review | Examine test code for risk mitigation |  | F | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed | Base
| Calculation |  |  | Not tested | New
| Data |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
Historical Data
Current Assignment: |  | Assignment 6 | CAAssignment 6.xls
Immediate Past Assignment: |  | Assignment6 | Assignment6
As of the end of |  |  | Assignment6
|  | Assignment6 | Assignment6 | All previous
Program Size (LOC) |  | LOCp | LOCa | LOCa
Base code LOC count
Lines deleted from Base
Lines modified from Base
Lines added to Base
Reused lines
New lines of production code
Component Count |  | Plan | Actual | Actual to Date
Reused components |  |  |  | 0
Modified components |  |  |  | 0
New components |  |  |  | 0
|  | Assignment6 | Assignment6 | All previous
Time In Phase (minutes) |  | Ep | Ea | Ea | To Date %
Analyze |  |  |  |  | 0%
Architect |  |  |  |  | 0%
Plan project |  |  |  |  | 0%
Plan iteration |  |  |  |  | 0%
Construct |  |  |  |  | 0%
Refactor |  |  |  |  | 0%
Review |  |  |  |  | 0%
Integration test |  |  |  |  | 0%
Repattern |  |  |  |  | 0%
Postmortem |  |  |  |  | 0%
Sandbox |  |  |  |  | 0%
TOTAL |  |  |  | 0 | 0%
All previous
Changes traced to the activities below: |  |  |  | changes | To Date %
Analyze |  |  |  |  | 0%
Architect |  |  |  |  | 0%
Plan project |  |  |  |  | 0%
Plan iteration |  |  |  |  | 0%
Construct |  |  |  |  | 0%
Refactor |  |  |  |  | 0%
Review |  |  |  |  | 0%
Integration test |  |  |  |  | 0%
Repattern |  |  |  |  | 0%
Postmortem |  |  |  |  | 0%
Sandbox |  |  |  |  | 0%
TOTAL |  |  |  | 0 | 0%
App previous
Changes implemented in the activities below: |  |  |  | changes | To Date %
Analyze |  |  |  |  | 0%
Architect |  |  |  |  | 0%
Plan project |  |  |  |  | 0%
Plan iteration |  |  |  |  | 0%
Construct |  |  |  |  | 0%
Refactor |  |  |  |  | 0%
Review |  |  |  |  | 0%
Integration test |  |  |  |  | 0%
Repattern |  |  |  |  | 0%
Postmortem |  |  |  |  | 0%
Sandbox |  |  |  |  | 0%
TOTAL |  |  |  | 0 | 0%
Size Matrix (LOC/Method)
| Lower | Mid | Upper
VS
S
M
L
VL
Project History
| New and Changed LOC |  |  | Effort
Project Name | Raw LOC | Planned LOC | Actual LOC | Estimated Time | Actual Time | LOCa/LOCr | Ea/LOCa
1.xls | 0 |  |  |  |  | 0 | 0
CA02 | 0 |  |  |  |  | 0 | 0
3.xls | [5 empty] | 0 | 0
CA04 | 0 |  |  |  |  | 0 | 0
CA05 |  | 0 | 0 | 0 | 0 | 0 | 0
Project Trends
Productivity= |  | LOC/hr
Average size= |  | LOC/method
Component History
Component Name |  | Total LOC | Method Count | Type | Size | LOC/method | ln(LOC/meth)
dispatch |  |  |  | Logic | -
|  |  |  | - | -
|  |  |  | - | - |  |  | `
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
[6 empty] | Average= | 0
[6 empty] | Std= | 0
Note on C57: Estimate the number of new lines of code that provide new functionality to meet the specifications of this assignment.
Note on C61: Estimate of the number of previously-written components that require modification
Note on C62: Estimate of the number of entirely new components

## Review (hidden)
Review
Standards
Start date: | 2000-01-01 |  | Grades: |  |  | AA
End date: | 2020-01-01 |  |  |  |  | A
Phases: | Analysis |  |  |  |  | AB
| Architecture |  |  |  |  | B
| Planning |  |  |  |  | BC
| Construction |  |  |  |  | C
| Refactoring |  |  |  |  | CD
| Review |  |  |  |  | D
| Integration Test |  |  |  |  | F
Postmortem
Sandbox
Defect Types: | Documentation |  | Iteration |  |  | NA
| Build |  |  |  |  | 1
| Product syntax |  |  |  |  | 2
| Product logic |  |  |  |  | 3
| Product interface |  |  |  |  | 4
| Product checking |  |  |  |  | 5
| Test syntax |  |  |  |  | 6
| Test logic |  |  |  |  | 7
| Test interface |  |  |  |  | 8
| Test checking |  |  |  |  | 9
| Bad Smell |  |  |  |  | 10
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
Sizes: | VS
S
M
L
VL
Defect Pareto Analysis (taken from all defects to date)
| Type | Description |  | Count of Occurrences | %
| Requirements Change | Changes to requirements
| Requirements Clarification | Clarifications to requirements
| Product syntax | Syntax flaws in the deliverable product
| Product logic | Logic flaws in the deliverable product
| Product interface | Flaws in the interface of a component of the deliverable product
| Product checking | Flaws with boundary/type checking within a component of the deliverable product
| Test syntax | Syntax flaws in the test code
| Test logic | Logic flaws in the test code
| Test interface | Flaws in the interface of a component of the test code
| Test checking | Flaws with boundary/type checking within a component of the test code
| Bad Smell | Refactoring changes (please note the bad smell in the defect description)
|  |  | Total | 0 | 0%
Code Review Checklist
| Item |  |  | Number of times this item detected a defect during review

## Acceptance
Constants | [5 empty] | 0
Start date: | 36526 |  |  | Grades: | AA | 1 | 0
End date: | 73051 |  |  |  | A | 0.95 | 0
Phases: | Analyze |  | Identifying customer needs |  | AB | 0.9 | 0
| Architect |  | High-level design |  | B | 0.85 | 0
| Plan project |  | Determine actions/effort for project duration |  | BC | 0.8 | 0
| Plan iteration |  | Determine actions/effort this iteration |  | C | 0.75 | 0
| Construct |  | Low-level design, coding, unit testing |  | CD | 0.7 | 43896
| Refactor |  | Restructure internal design |  | D | 0.65 | 43897
| Review |  | Examine test code for risk mitigation |  | F | 0.5 | 43898
| Integration test |  | End-to-end test of components to date |  |  |  | 43899
| Repattern |  | Restructure external design |  |  |  | 43900
| Postmortem |  | Capture post-development statistics |  |  |  | 43901
| Sandbox |  | Prove ideas, try concepts |  |  |  | 43902
43903
43904
43905
#REF!
Defect Types: | Requirements Change |  | Changes to requirements | Iteration | NA | did not follow | #REF!
| Requirements Clarification |  | Clarifications to requirements |  | 1 | very painful | #REF!
| Product syntax |  | Syntax flaws in the deliverable product |  | 2 | painful | #REF!
| Product logic |  | Logic flaws in the deliverable product |  | 3 | neutral | #REF!
| Product interface |  | Flaws in the interface of a component of the deliverable product |  | 4 | helpful | #REF!
| Product checking |  | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful | #REF!
| Test syntax |  | Syntax flaws in the test code |  | 6 |  | #REF!
| Test logic |  | Logic flaws in the test code |  | 7 |  | #REF!
| Test interface |  | Flaws in the interface of a component of the test code |  | 8 |  | #REF!
| Test checking |  | Flaws with boundary/type checking within a component of the test code |  | 9 |  | #REF!
| Bad Smell |  | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0 | #REF!
Y/N: | Yes |  |  |  | Passed | 0 | #REF!
| No |  |  |  | Passed with issues | 0 | 43919
Proxy Types: | - |  |  |  | Failed | Base | 43920
| Calculation |  |  |  | Not tested | New | 43921
| Data |  |  |  | Not applicable | Reusable | 43922
| I/O | [5 empty] | 43923
| Logic | [5 empty] | 43924
43925
Sizes: | VS |  | S | M | L | VL | VS
upper | -1.5 |  | -0.5 | 0.5 | 1.5 | 99999 | S
mid | -2 |  | -1 | 0 | 1 | 2 | M
lower | 0 |  | -1.5 | -0.5 | 0.5 | 1.5 | L
| 0 |  | 0 | 0 | 0 |  | VL
Acceptance Test Report
Use this worksheet to record tests that, if passed, tell you that your software is complete. It is not a chronology, so do not list a history of tests. List only tests that are directly linked to requirements (in other words, do not list tests for methods or components that you create over and above what is required to fulfill the specified interface definition -- these tests will appear in your individual unit test files). Write the expected results at planning time. Modify if necessary later. Don’t write actual results in advance.
Requirements:
op=create
op=status
op=place
op=next
Requirement | Test Description | Test | Expected Results |  | Actual Results | Issues
op=create | happy path test 010: nominal light, nominal dark, nominal blank, nominal size | http://localhost:5000/othello?op=create&light=6&dark=5&blank=1&size=10 | {'board': [1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 6, 5, 1, 1, 1, 1, 1, 1, 1, 1, 5, 6, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1], 'tokens': {'light': 6, 'dark': 5, 'blank': 1}, 'status': 'ok', 'integrity': 'd0f18c5b412ab1dbf89da19baa33cc35f4a7dd0619ce7b7dcb2381d2cb14a412'} |  | Passed
op=create | happy path test 020: high bound light, nominal dark, nominal blank, nominal size | http://localhost:5000/othello?op=create&light=9&dark=5&blank=1&size=10 | {'board': [1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 9, 5, 1, 1, 1, 1, 1, 1, 1, 1, 5, 9, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1], 'tokens': {'light': 9, 'dark': 5, 'blank': 1}, 'status': 'ok', 'integrity': '723c769319c6529cf8520336232a9e5d281be77df1455c6ceb10a5d1d4733236'} |  | Passed
op=create | happy path test 021: low bound light, nominal dark, nominal blank, nominal size | http://localhost:5000/othello?op=create&light=0&dark=5&blank=1&size=10 | {'board': [1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 0, 5, 1, 1, 1, 1, 1, 1, 1, 1, 5, 0, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1, 1], 'tokens': {'light': 0, 'dark': 5, 'blank': 1}, 'status': 'ok', 'integrity': '4bd2efa7e0d5f13551f7277950e45b6fcfe7d5159b80823a5dcbdf57abb4d83a'} |  | Passed
op=create | happy path test 022: missing light, nominal dark, nominal blank, nominal size | http://localhost:5000/othello?op=create&dark=5&blank=3&size=10 | {'board': [3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 1, 5, 3, 3, 3, 3, 3, 3, 3, 3, 5, 1, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3, 3], 'tokens': {'light': 1, 'dark': 5, 'blank': 3}, 'status': 'ok', 'integrity': 'f211a92f576794a821bb24f359739b8b42a6a16634005a1e4b32313a6575e2be'} |  | Passed
op=create | happy path test 030: nominal light, high bound dark, nominal blank, nominal size | http://localhost:5000/othello?op=create&light=3&dark=9&blank=4&size=10 | {'board': [4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 3, 9, 4, 4, 4, 4, 4, 4, 4, 4, 9, 3, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4], 'tokens': {'light': 3, 'dark': 9, 'blank': 4}, 'status': 'ok', 'integrity': 'a3718ffbc2f822320ee4db10c269a9749859b9952db13ff6b289a6ebd6ce42c6'} |  | Passed
op=create | happy path test 031: nominal light, low bound dark, nominal blank, nominal size | http://localhost:5000/othello?op=create&light=3&dark=0&blank=4&size=10 | {'board': [4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 3, 0, 4, 4, 4, 4, 4, 4, 4, 4, 0, 3, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4], 'tokens': {'light': 3, 'dark': 0, 'blank': 4}, 'status': 'ok', 'integrity': '7bf98e8385a158097f52361dac139bb5882f3eaa48e8146d72d65de5981d2e5e'} |  | Passed
op=create | happy path test 032: nominal light, missing dark, nominal blank, nominal size | http://localhost:5000/othello?op=create&light=3&blank=4&size=10 | {'board': [4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 3, 2, 4, 4, 4, 4, 4, 4, 4, 4, 2, 3, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4, 4], 'tokens': {'light': 3, 'dark': 2, 'blank': 4}, 'status': 'ok', 'integrity': '71f91a7d487c9e9ad69a43269c6a90c449f97fd93848b8493e47a2f6054e7c82'} |  | Passed
op=create | happy path test 040: nominal light, nominal dark, high bound blank, nominal size | http://localhost:5000/othello?op=create&light=3&dark=4&blank=9&size=10 | {'board': [9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 3, 4, 9, 9, 9, 9, 9, 9, 9, 9, 4, 3, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9, 9], 'tokens': {'light': 3, 'dark': 4, 'blank': 9}, 'status': 'ok', 'integrity': '5b4c82af0cf6a72ab1938b8e5a3c1ce413b9db583d0f974703954427413021d0'} |  | Passed
op=create | happy path test 041: nominal light, nominal dark, low bound blank, nominal size | localhost:5000/othello?op=create&light=3&dark=4&blank=0&size=10 | {'board': [0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 3, 4, 0, 0, 0, 0, 0, 0, 0, 0, 4, 3, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0], 'tokens': {'light': 3, 'dark': 4, 'blank': 0}, 'status': 'ok', 'integrity': 'eeaa1d4229234a1453901319e7f584a337595d6d332a22a76c4aae8888cde9d6'} |  | Passed
op=create | happy path test 042: nominal light, nominal dark, missingd blank, nominal size | localhost:5000/othello?op=create&light=3&dark=4&size=10 | {'board': [0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 3, 4, 0, 0, 0, 0, 0, 0, 0, 0, 4, 3, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0], 'tokens': {'light': 3, 'dark': 4, 'blank': 0}, 'status': 'ok', 'integrity': 'eeaa1d4229234a1453901319e7f584a337595d6d332a22a76c4aae8888cde9d6'} |  | Passed
op=create | happy path test 050: nominal light, nominal dark, nominal blank, high bound size | http://localhost:5000/othello?op=create&light=3&dark=4&blank=5&size=16 | {'board': [5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 3, 4, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 4, 3, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5], 'tokens': {'light': 3, 'dark': 4, 'blank': 5}, 'status': 'ok', 'integrity': '682b1bac788017f23b846862ce44f2c3efe03a22f49de36085e0e57fc6957416'} |  | Passed
op=create | happy path test 051: nominal light, nominal dark, nominal blank, low bound size | http://localhost:5000/othello?op=create&light=3&dark=4&blank=5&size=6 | {'board': [5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 3, 4, 5, 5, 5, 5, 4, 3, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5], 'tokens': {'light': 3, 'dark': 4, 'blank': 5}, 'status': 'ok', 'integrity': 'b87b212e557d1dc1080f1c6e380bab404ae8cffa048b86e649e54c620f0d9c6a'} |  | Passed
op=create | happy path test 052: nominal light, nominal dark, nominal blank, missing size | http://localhost:5000/othello?op=create&light=3&dark=4&blank=5 | {'board': [5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 3, 4, 5, 5, 5, 5, 5, 5, 4, 3, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5, 5], 'tokens': {'light': 3, 'dark': 4, 'blank': 5}, 'status': 'ok', 'integrity': '306a2474c8f8b41c9e31af0fe360f9fcaf3531b3b4a1c3624acd8fbc2530b02e'} |  | Passed
op=create | happy path test 060: all parameters are defaulted | http://localhost:5000/othello?op=create | {'board': [0,0,0,0,0,0,0,0, 0,0,0,0,0,0,0,0, 0,0,0,0,0,0,0,0, 0,0,0,1,2,0,0,0, 0,0,0,2,1,0,0,0, 0,0,0,0,0,0,0,0, 0,0,0,0,0,0,0,0, 0,0,0,0,0,0,0,0],'tokens': {'light': 1,'dark': 2, 'blank': 0},'integrity': 'db24b170e77c8bef5416f5d39e1fb94b82245089416b95305756043dd195fcef','status':'ok'} |  | Passed
op=create | happy path test 070: extraneous parameters are ignored | http://localhost:5000/othello?op=create&extra=1234 | {'board': [0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 1, 2, 0, 0, 0, 0, 0, 0, 2, 1, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0, 0], 'tokens': {'light': 1, 'dark': 2, 'blank': 0}, 'status': 'ok', 'integrity': 'b11fcf5f9ac9d3b8cea8085208e210182a8d6b73a84028562ab2c87d190b9ada'} |  | Passed
op=create | sad path test 900: above bound light, nominal dark, nominal blank, nominal size | http://localhost:5000/othello?op=create&light=10 | {'status': 'error: <xxx>'}, where <xxx> is some message |  | Passed
op=create | sad path test 901: below bound light, nominal dark, nominal blank, nominal size | http://localhost:5000/othello?op=create&light=-1 | {'status': 'error: <xxx>'}, where <xxx> is some message |  | Passed
op=create | sad path test 902: non-integer light, nominal dark, nominal blank, nominal size | http://localhost:5000/othello?op=create&light=w | {'status': 'error: <xxx>'}, where <xxx> is some message |  | Passed
op=create | sad path test 903: null light, nominal dark, nominal blank, nominal size | http://localhost:5000/othello?op=create&light= | {'status': 'error: <xxx>'}, where <xxx> is some message |  | Passed
op=create | sad path test 910: nominal light, above bound dark, nominal blank, nominal size | http://localhost:5000/othello?op=create&dark=10 | {'status': 'error: <xxx>'}, where <xxx> is some message |  | Passed
op=create | sad path test 911: nominal light, below bound dark, nominal blank, nominal size | http://localhost:5000/othello?op=create&dark=-1 | {'status': 'error: <xxx>'}, where <xxx> is some message |  | Passed
op=create | sad path test 912: nominal light, non-integer dark, nominal blank, nominal size | http://localhost:5000/othello?op=create&dark=d | {'status': 'error: <xxx>'}, where <xxx> is some message |  | Passed
op=create | sad path test 913: nominal light, null dark, nominal blank, nominal size | http://localhost:5000/othello?op=create&dark= | {'status': 'error: <xxx>'}, where <xxx> is some message |  | Passed
op=create | sad path test 920: nominal light, nominal dark, above bound blank, nominal size | http://localhost:5000/othello?op=create&blank=10 | {'status': 'error: <xxx>'}, where <xxx> is some message |  | Passed
op=create | sad path test 921: nominal light, nominal dark, below bound blank, nominal size | http://localhost:5000/othello?op=create&blank=-1 | {'status': 'error: <xxx>'}, where <xxx> is some message |  | Passed
op=create | sad path test 922: nominal light, nominal dark, non-integer blank, nominal size | http://localhost:5000/othello?op=create&blank=b | {'status': 'error: <xxx>'}, where <xxx> is some message |  | Passed
op=create | sad path test 923: nominal light, nominal dark, null blank, nominal size | http://localhost:5000/othello?op=create&blank= | {'status': 'error: <xxx>'}, where <xxx> is some message |  | Passed
op=create | sad path test 930: nominal light, nominal dark, nominal blank, above bound size | http://localhost:5000/othello?op=create&size=17 | {'status': 'error: <xxx>'}, where <xxx> is some message |  | Passed
op=create | sad path test 931: nominal light, nominal dark, nominal blank, below bound size | http://localhost:5000/othello?op=create&size=5 | {'status': 'error: <xxx>'}, where <xxx> is some message |  | Passed
op=create | sad path test 933: nominal light, nominal dark, nominal blank, odd size | http://localhost:5000/othello?op=create&blank=9 | {'status': 'error: <xxx>'}, where <xxx> is some message |  | Passed
op=create | sad path test 932: nominal light, nominal dark, nominal blank, non-integer size | http://localhost:5000/othello?op=create&size=1.2 | {'status': 'error: <xxx>'}, where <xxx> is some message |  | Passed
op=create | sad path test 933: nominal light, nominal dark, nominal blank, null size | http://localhost:5000/othello?op=create&size= | {'status': 'error: <xxx>'}, where <xxx> is some message |  | Passed
op=create | sad path test 940: nominal light, dark = light, nominal blank, nominal size | http://localhost:5000/othello?op=create&light=5&dark=5&blank=0 | {'status': 'error: <xxx>'}, where <xxx> is some message |  | Passed
op=create | sad path test 941: nominal light, nominal dark, blank = light, nominal size | http://localhost:5000/othello?op=create&light=5&dark=2&blank=5 | {'status': 'error: <xxx>'}, where <xxx> is some message |  | Passed
op=create | sad path test 940: nominal light, nominal dark, blank = dark, nominal size | http://localhost:5000/othello?op=create&light=1&dark=2&blank=2 | {'status': 'error: <xxx>'}, where <xxx> is some message |  | Passed
Note on A50: Establish traceability between the tests and requirements.
Note on B50: Defines observable tests that have quantifiable resutls.
Note on D50: Specifies the result that that the test is anticipated to produce.
Note on F50: Defines the result of running the test in relation to the expected result.
Note on G50: Required whenthe actual result is "Passed with issues"; optional otherwise. An "issue" is a side-effect that is not part of the specified test.

## Map (hidden)
Sceneario-Component Map
X
Component Names:
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## Architecture (hidden)
Architecture
Use this worksheet to describe components required to implement the specifications. List new components and base components. Do not include extraneous components. | Use this worksheet to describe components required to implement the specifications. List new components and base components. Do not include extraneous components.
Standards
| Start date: | 2000-01-01
| End date: | 2010-01-01
| Phases: | Planning
Design
Design Review
Code
Code Review
Compile
Test
Postmortem
| Defect Types: | Documentation
Syntax
Build, Package
Assignment
Interface
Checking
Data
Function
System
Environment
| Y/N: | Yes
No
| Component Types: | Calculation
Data
I/O
Logic
| Design Approaches: | Object-oriented
Functional
| Sizes: | VS
S
M
L
VL
| Duration: | LOCe x T
LOCa x T
Productivity
1 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
2 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
3 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
4 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
5 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
6 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
7 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
8 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
9 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
10 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Note on B43: Identifying name for this design class or function.
Note on B44: Indicate if this design component will follow an object-oriented approach or a functional approach.
Note on B45: Superclass of this design component. Leave blank if no superclass.
Note on B46: Attributes (e.g., public fields, public constants) associated with this design component. OPTIONAL
Note on B47: Standard category of the design component.
Note on B48: List components that this component calls upon to fulfill its purpose.
Note on B49: Description of the operations of this design component. If your are taking an object-oriented approach, list the methods associated with this object in the "operation" column. If you are taking a functional approach, list the component name in the "operation" column. Note: an object-oriented approach may result in zero or more operations; a functional approach will have only one operation listed.

## Estimation (hidden)
Size Estimate
Constants |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Start date: | 36526 |  | Grades: | AA | 1 | 0 | 43905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
End date: | 73051 |  |  | A | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Phases: | Analyze | Identifying customer needs |  | AB | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Architect | High-level design |  | B | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Plan project | Determine actions/effort for project duration |  | BC | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construct | Low-level design, coding, unit testing |  | CD | 0.7 | 43896 | 0 | 0 | AM | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Refactor | Restructure internal design |  | D | 0.65 | 43897 | 1 | 5 | PM | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Review | Examine test code for risk mitigation |  | F | 0.5 | 43898 | 2 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Integration test | End-to-end test of components to date |  |  |  | 43899 | 3 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Repattern | Restructure external design |  |  |  | 43900 | 4 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Postmortem | Capture post-development statistics |  |  |  | 43901 | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Sandbox | Prove ideas, try concepts |  |  |  | 43902 | 6 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 43903 | 7 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 43904 | 8 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 43905 | 9 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 43906 | 10 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow | 43907 | 11 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful | 43908 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful | 43909 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral | 43910 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful | 43911 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful | 43912 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test syntax | Syntax flaws in the test code |  | 6 |  | 43913 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test logic | Logic flaws in the test code |  | 7 |  | 43914 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test interface | Flaws in the interface of a component of the test code |  | 8 |  | 43915 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9 |  | 43916 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0 | 43917 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Y/N: | Yes |  |  | Passed | 0 | 43918 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| No |  |  | Passed with issues | 0 | 43919 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Proxy Types: | - |  |  | Failed | Base | 43920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Calculation |  |  | Not tested | New | 43921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Data |  |  | Not applicable | Reusable | 43922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| I/O |  |  |  |  | 43923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Logic |  |  |  |  | 43924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 43925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sizes: | VS | S | M | L | VL | VS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999 | S | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
mid | -2 | -1 | 0 | 1 | 2 | M | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5 | L | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  | VL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
<-- Mandatory |  | ✔ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Estimated | [10 empty] | Actual
|  |  | Changes to existing code | [5 empty] | New code |  |  |  |  | Changes to existing code | [5 empty] | New code
Component | Type | Relative Size | Base LOC count | Number of LOC modified in base | Number of LOC added to base | Number of LOC deleted from base | Number of base LOC contributing to effort |  | Number of new methods added | LOC/Method | Number of new LOC contributing to effort | Total number of LOC contributing to effort (LOCr) |  | Base LOC count | Number of LOC modified in base | Number of LOC added to base | Number of LOC deleted from base | Number of base LOC contributing to effort |  | Number of new methods added | LOC/Method | Number of new LOC contributing to effort | Total number of LOC contributing to effort (LOCa) | Is this component reusable?
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
[7 empty] | 0 |  |  |  | 0 | 0 | [5 empty] | 0 |  |  |  |  | 0
Totals |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Size Calculation
0
0
0
|  | 0 | Low
Effort Calculation
0
0
0
0
|  | 0 | Low
Estimation: | LOCr= |  | 0
| LOCp= | [12 empty] | Actual: | LOCa= | 0
Ep=
Rationale for override:

## ArcEstimation (hidden)
Size Estimate
Standards
Start date: | 2000-01-01 |  |  | Grades: | AA
End date: | 2020-01-01 |  |  |  | A
Phases: | Planning |  |  |  | AB
| Architecture |  |  |  | B
| Construction |  |  |  | BC
| Refactoring |  |  |  | C
| Integration Test |  |  |  | CD
| Review |  |  |  | D
| Sandbox |  |  |  | F
Postmortem
Defect Types: | Documentation
| Build |  |  | Type | Event
| Product syntax |  |  |  | Response
| Product logic |  |  | Origin | Test Component
| Product interface |  |  |  | Blackbox
| Product checking |  |  |  | User
| Test syntax |  |  |  | External Component (specify)
| Test logic |  |  | Op Spec type | User
| Test interface |  |  |  | Interface
Test checking
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
Metaphysics: | Object-oriented
Functional
Sizes: | VS
S
M
L
VL
Duration: | LOCe x T
LOCa x T
Productivity
| Estimated |  |  |  |  | Actual
Base Components | Base LOC | Deleted LOC | Modified LOC | Added LOC |  | Base LOC | Deleted LOC | Modified LOC | Added LOC
Totals | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Estimated |  |  |  |  | Actual
New Components | Method Count | LOCr | Reuseable? |  |  | Method Count | LOCa | Reusable?
Totals |  | 0 |  |  |  |  | 0
Actual
Reused Parts | LOC
Totals | 0
Size Calculation
#REF!
0
#REF!
|  | 0 | Low
Effort Calculation
0
#REF!
#REF!
#REF!
|  | 0 | Low
Estimation | LOCr= |  | 0
| LOCp= |  | 0 |  |  | LOCa= | 0
| Ep= |  | 0
Rationale for override:
Note on G66: Indicate only new methods and LOC that resulted from effort. Do not count items that were previously base code and were refactored into new components.

## Plan
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analyze | Identifying customer needs |  | AB | 0.9
| Architect | High-level design |  | B | 0.85
| Plan project | Determine actions/effort for project duration |  | BC | 0.8
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75
| Construct | Low-level design, coding, unit testing |  | CD | 0.7
| Refactor | Restructure internal design |  | D | 0.65
| Review | Examine test code for risk mitigation |  | F | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed | Base
| Calculation |  |  | Not tested | New
| Data |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
<-- Mandatory |  | ✔
Project Plan Summary
Use this worksheet to record how much production code you plan to write and the amount of time to write it. Record the actual size once the project is complete. The actual time will be calculated from the Time Log. Please note that you are not being evaluated on how close your planned values to your actual values.
Program Size (LOC) |  | Plan | Actual | To Date
Base code LOC count |  |  |  | 0
Lines deleted from Base |  |  |  | 0
Lines modified from Base |  |  |  | 0
Lines added to Base |  |  |  | 0
Reused lines |  |  |  | 0
New lines of production code |  | 200 | 88 | 88
Component Count |  | Plan | Actual | To Date
Reused components |  |  |  | 0
Modified components |  |  |  | 0
New components |  |  |  | 0
Time In Phase (minutes) |  | Plan | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 35 | 35 | 5.344%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 20 | 20 | 3.053%
Construct |  |  | 315 | 315 | 48.09%
Refactor |  |  | 0 | 0 | 0%
Review |  |  | 20 | 20 | 3.053%
Integration test |  |  | 235 | 235 | 35.88%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 10 | 10 | 1.527%
Sandbox |  |  | 20 | 20 | 3.053%
TOTAL |  | 720 | 655 | 655 | 100%
Changes Identified |  |  | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 0 | 0 | 0%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 7 | 7 | 100%
Refactor |  |  | 0 | 0 | 0%
Review |  |  | 0 | 0 | 0%
Integration test |  |  | 0 | 0 | 0%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 7 | 7 | 100%
Changes Implemented |  |  | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 0 | 0 | 0%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 2 | 2 | 28.57%
Refactor |  |  | 0 | 0 | 0%
Review |  |  | 1 | 1 | 14.29%
Integration test |  |  | 4 | 4 | 57.14%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 7 | 7 | 100%
Note on C48: Number of lines used from previously-written code
Note on C49: Estimate of the number of lines deleted from previously-written code
Note on C50: Estimated of the number of lines modified from previously-written code
Note on C51: Estimate of the number of lines added to previously-written code to bring it to the point where new functionality can be added
Note on C52: Count of the number of lines of reused source code
Note on C53: Estimate the number of new lines of production code that provide new functionality to meet the specifications of this assignment.
Note on C56: Number of reusable components that will be reused.
Note on C57: Estimate of the number of previously-delivered components that will be used.
Note on C58: Estimate of the number of new components to be built.
Note on C72: Estimate in minutes how much time you plan to expend on this assignment.

## Iterations (hidden)
Iterations
Standards
Start date: | 2000-01-01
End date: | 2025-01-01
Phases: | Planning
Design
Design Review
Code
Code Review
Compile
Test
Postmortem
Documentation
Syntax
Defect Types: | Build, Package
Assignment
Interface
Checking
Data
Function
System
Environment
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
|  |  | estimation methods | A
Sizes: | VS |  |  | B
| S |  |  | C
| M |  |  | D
L
VL
Duration: | LOCe x T
LOCa x T
Productivity
Component-Iteration Map
| Component | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 5 | Iteration 6 | Iteration 7 | Iteration 8 | Iteration 9 | Iteration 10
Base Components | [11 empty] | 0
0
0
0
0
0
0
0
0
0
New Components | [11 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Number of tasks: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Effort: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS
| Iteration Number | Planned Effort (minutes) | Cumulative Planned Effort | Planned Velocity | Cumulative Planned Velocity | Planned Completion Date
| 1 |  | 0 |  | 0
| 2 |  | 0 |  | 0
| 3 |  | 0 |  | 0
| 4 |  | 0 |  | 0
| 5 |  | 0 |  | 0
| 6 |  | 0 |  | 0
| 7 |  | 0 |  | 0
| 8 |  | 0 |  | 0
| 9 |  | 0 |  | 0
| 10 |  | 0 |  | 0
Calendar
| Day # | Date | Available Minutes | Cumulative Minutes | Planned Velocity | Cumulative Planned Velocity
| 1 | due date - 24 |  | 0 |  | 0
| 2 | due date - 23 |  | 0 |  | 0
| 3 | due date - 22 |  | 0 |  | 0
| 4 | due date - 21 |  | 0 |  | 0
| 5 | due date - 20 |  | 0 |  | 0
| 6 | due date - 19 |  | 0 |  | 0
| 7 | due date - 18 |  | 0 |  | 0
| 8 | due date - 17 |  | 0 |  | 0
| 9 | due date - 16 |  | 0 |  | 0
| 10 | due date - 15 |  | 0 |  | 0
| 11 | due date - 14 |  | 0 |  | 0
| 12 | due date - 13 |  | 0 |  | 0
| 13 | due date - 12 |  | 0 |  | 0
| 14 | due date - 11 |  | 0 |  | 0
| 15 | due date - 10 |  | 0 |  | 0
| 16 | due date - 9 |  | 0 |  | 0
| 17 | due date - 8 |  | 0 |  | 0
| 18 | due date - 7 |  | 0 |  | 0
| 19 | due date - 6 |  | 0 |  | 0
| 20 | due date - 5 |  | 0 |  | 0
| 21 | due date - 4 |  | 0 |  | 0
| 22 | due date - 3 |  | 0 |  | 0
| 23 | due date - 2 |  | 0 |  | 0
| 24 | due date - 1 |  | 0 |  | 0
| 25 | due date |  | 0 |  | 0
| 26 | due date + 1 |  | 0 |  | 0
| 27 | due date + 2 |  | 0 |  | 0
| 28 | due date + 3 |  | 0 |  | 0
| 29 | due date + 4 |  | 0 |  | 0
| 30 | due date + 5 |  | 0 |  | 0
| 31 | due date + 6 |  | 0 |  | 0
| 32 | due date + 7 |  | 0 |  | 0
| 33 | due date + 8 |  | 0 |  | 0
| 34 | due date + 9 |  | 0 |  | 0
| 35 | due date + 10 |  | 0 |  | 0
| 36 | due date + 11 |  | 0 |  | 0
| 37 | due date + 12 |  | 0 |  | 0
| 38 | due date + 13 |  | 0 |  | 0
| 39 | due date + 14 |  | 0 |  | 0
| 40 | due date + 15 |  | 0 |  | 0
| 41 | due date + 16 |  | 0 |  | 0
| 42 | due date + 17 |  | 0 |  | 0

## Summary (hidden)
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analyze | Identifying customer needs |  | AB | 0.9
| Architect | High-level design |  | B | 0.85
| Plan project | Determine actions/effort for project duration |  | BC | 0.8
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75
| Construct | Low-level design, coding, unit testing |  | CD | 0.7
| Refactor | Restructure internal design |  | D | 0.65
| Review | Examine test code for risk mitigation |  | F | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed | Base
| Calculation |  |  | Not tested | New
| Data |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
<-- Mandatory |  | ✔
Project Plan Summary
Use this worksheet to show how much production code you plan to write and the amount of time to write it. Values are extracted from the Estimation tab.
Program Size (LOC) |  | Plan | Actual | To Date
LOC |  | 0 | 0 | 0
LOCa |  |  |  | 0
Lines added to Base |  | 0 |  | 0
Reused lines |  |  |  | 0
New lines of production code |  | 0 |  | 0
Component Count |  | Plan | Actual | To Date
Reused components |  |  |  | 0
Modified components |  |  |  | 0
New components |  |  |  | 0
Time In Phase (minutes) |  | Plan | Actual | Actual to Date | Actual to Date %
Analyze |  | 0 | 35 | 35 | 5.344%
Architect |  | 0 | 0 | 0 | 0%
Plan project |  | 0 | 0 | 0 | 0%
Plan iteration |  | 0 | 20 | 20 | 3.053%
Construct |  | 0 | 315 | 315 | 48.09%
Refactor |  | 0 | 0 | 0 | 0%
Review |  | 0 | 20 | 20 | 3.053%
Integration test |  | 0 | 235 | 235 | 35.88%
Repattern |  | 0 | 0 | 0 | 0%
Postmortem |  | 0 | 10 | 10 | 1.527%
Sandbox |  | 0 | 20 | 20 | 3.053%
TOTAL |  | 0 | 655 | 655 | 100%
Changes Identified |  |  | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 0 | 0 | 0%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 7 | 7 | 100%
Refactor |  |  | 0 | 0 | 0%
Review |  |  | 0 | 0 | 0%
Integration test |  |  | 0 | 0 | 0%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 7 | 7 | 100%
Changes Implemented |  |  | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 0 | 0 | 0%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 2 | 2 | 28.57%
Refactor |  |  | 0 | 0 | 0%
Review |  |  | 1 | 1 | 14.29%
Integration test |  |  | 4 | 4 | 57.14%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 7 | 7 | 100%
Note on C50: Estimate of the number of lines added to previously-written code to bring it to the point where new functionality can be added
Note on C51: Count of the number of lines of reused source code
Note on C52: Estimate the number of new lines of production code that provide new functionality to meet the specifications of this assignment.
Note on C55: Number of reusable components that will be reused.
Note on C56: Estimate of the number of previously-delivered components that will be used.
Note on C57: Estimate of the number of new components to be built.

## PlanSummary (hidden)
Project Plan Summary
Standards
Start date: | 2000-01-01 |  | Grades: | AA
End date: | 40179 |  |  | A
Phases: | Analysis |  |  | AB
| Architecture |  |  | B
| Planning |  |  | BC
| Construction |  |  | C
| Refactoring |  |  | CD
| Review |  |  | D
| Integration Test |  |  | F
Postmortem
Sandbox
Defect Types: | Documentation |  | Iteration | NA
| Build |  |  | 1
| Product syntax |  |  | 2
| Product logic |  |  | 3
| Product interface |  |  | 4
| Product checking |  |  | 5
| Test syntax |  |  | 6
| Test logic |  |  | 7
| Test interface |  |  | 8
| Test checking |  |  | 9
| Bad Smell |  |  | 10
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
Sizes: | VS
S
M
L
VL
|  | Plan | Actual | To Date
Program Size (LOC)
Base code LOC count |  | 0 | 0 | 0
Lines deleted from Base |  | 0 | 0 | 0
Lines modified from Base |  | 0 | 0 | 0
Lines added to Base |  | 0 | 0 | 0
Reused lines |  | #REF! | 0 | 0
New lines of production code |  | #REF! | 0 | 0
|  | Plan | Actual | To Date | To Date %
Time In Phase (minutes)
Analyze |  | 0 | 35 | 35 | 350%
Architect |  | 0 | 0 | 0 | 0%
Plan project |  | 0 | 0 | 0 | 0%
Plan iteration |  | 0 | 20 | 20 | 200%
Construct |  | 0 | 315 | 315 | 3150%
Refactor |  | 0 | 0 | 0 | 0%
Review |  | 0 | 20 | 20 | 200%
Integration test |  | 0 | 235 | 235 | 2350%
Repattern |  | 0 | 0 | 0 | 0%
Postmortem |  | 0 | 10 | 10 | 100%
Sandbox |  | 0 | 20 | 20 | 200%
TOTAL |  | 0 | 655 | 655 | 6550%
Changes traced to the activities below:
Analyze |  |  | 0 | 0
Architect |  |  | 0 | 0
Plan project |  |  | 0 | 0
Plan iteration |  |  | 0 | 0
Construct |  |  | 1 | 1
Refactor |  |  | 0 | 0
Review |  |  | 0 | 0
Integration test |  |  | 0 | 0
Repattern |  |  | 0 | 0
Postmortem |  |  | 0 | 0
Sandbox |  |  | 0 | 0
TOTAL |  |  | 1 | 1
Changes implemented in the activities below:
Analyze |  |  | 0 | 0
Architect |  |  | 0 | 0
Plan project |  |  | 0 | 0
Plan iteration |  |  | 0 | 0
Construct |  |  | 1 | 1
Refactor |  |  | 0 | 0
Review |  |  | 0 | 0
Integration test |  |  | 0 | 0
Repattern |  |  | 0 | 0
Postmortem |  |  | 0 | 0
Sandbox |  |  | 0 | 0
TOTAL |  |  | 1 | 1

## Change Log
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1 | 0 | 43905 | 0
End date: | 73051 |  |  | A | 0.95 | 0 | 0 | 0
Phases: | Analyze | Identifying customer needs |  | AB | 0.9 | 0 | 0 | 0
| Architect | High-level design |  | B | 0.85 | 0 | 0 | 0
| Plan project | Determine actions/effort for project duration |  | BC | 0.8 | 0 | 0 | 0
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75 | 0 | 0 | 0
| Construct | Low-level design, coding, unit testing |  | CD | 0.7 | 43896 | 1 | 0
| Refactor | Restructure internal design |  | D | 0.65 | 43897 | 2 | 5
| Review | Examine test code for risk mitigation |  | F | 0.5 | 43898 | 3 | 10
| Integration test | End-to-end test of components to date |  |  |  | 43899 | 4 | 15
| Repattern | Restructure external design |  |  |  | 43900 | 5 | 20
| Postmortem | Capture post-development statistics |  |  |  | 43901 | 6 | 25
| Sandbox | Prove ideas, try concepts |  |  |  | 43902 | 7 | 30
| Previous Project |  |  |  |  | 43903 | 8 | 35
[6 empty] | 43904 | 9 | 40
[6 empty] | 43905 | 10 | 45
[6 empty] | 43906 | 11 | 50
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow | 43907 | 12 | 55
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful | 43908 | 13 | 0
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful | 43909 | 14 | 0
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral | 43910 | 15 | 0
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful | 43911 | 16 | 0
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful | 43912 | 17 | 0
| Test syntax | Syntax flaws in the test code |  | 6 |  | 43913 | 18 | 0
| Test logic | Logic flaws in the test code |  | 7 |  | 43914 | 19 | 0
| Test interface | Flaws in the interface of a component of the test code |  | 8 |  | 43915 | 20 | 0
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9 |  | 43916 | 21 | 0
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0 | 43917 | 22 | 0
Y/N: | Yes |  |  | Passed | 0 | 43918 | 23 | 0
| No |  |  | Passed with issues | 0 | 43919 | 0 | 0
Proxy Types: | - |  |  | Failed | Base | 43920 | 0 | 0
| Calculation |  |  | Not tested | New | 43921 | 0 | 0
| Data |  |  | Not applicable | Reusable | 43922 | 0 | 0
| I/O |  |  |  |  | 43923 | 0 | 0
| Logic |  |  |  |  | 43924 | 0 | 0
[6 empty] | 43925 | 0 | 0
Sizes: | VS | S | M | L | VL | VS | 0 | 0
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999 | S | 0 | 0
mid | -2 | -1 | 0 | 1 | 2 | M | 0 | 0
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5 | L | 0 | 0
| 0 | 0 | 0 | 0 |  | VL | 0 | 0
[6 empty] | 0 | 0 | 0
<-- Mandatory |  | ✔ |  |  |  | 0 | 0 | 0
Change Log
Use this worksheet to record changes to made to artifacts after the project is underway. Record repairs to defects, as well as changes that result from requirements clarifications/changes.
|  | Change Designation | Description
|  | Requirements Change | Changes to requirements
|  | Requirements Clarification | Clarifications to requirements
|  | Product syntax | Syntax flaws in the deliverable product
|  | Product logic | Logic flaws in the deliverable product
|  | Product interface | Flaws in the interface of a component of the deliverable product
|  | Product checking | Flaws with boundary/type checking within a component of the deliverable product
|  | Test syntax | Syntax flaws in the test code
|  | Test logic | Logic flaws in the test code
|  | Test interface | Flaws in the interface of a component of the test code
|  | Test checking | Flaws with boundary/type checking within a component of the test code
|  | Bad Smell | Refactoring changes (please note the bad smell in the defect description)
Change Number | Date Of Change | Change Type | Activity Where Injected | Iteration Where Injected | Activity Where Removed | Iteration Where Removed | Fix Time | Reference To A Previous Change | Description
1 | 2020-03-13 | Product checking | Construct | 1 | Construct | 1 | 60 |  | Had to redo how the program validated inputs
2 | 2020-03-13 | Test checking | Construct | 1 | Construct | 1 | 5 |  | Upper bound for light/dark/blank was at 8 instead of 9
3 | 2020-03-14 | Product logic | Construct | 1 | Review | 1 | 20 |  | My nextPlayer value was set to 2 instead of the dark value
4 | 2020-03-14 | Test checking | Construct | 1 | Integration test | 1 | 5 |  | Upper bound for size was at 15 instead of 16
5 | 2020-03-14 | Test checking | Construct | 1 | Integration test | 1 | 20 |  | Input values were read in as strings from microservice so they must be converted to int
6 | 2020-03-15 | Test checking | Construct | 1 | Integration test | 1 | 20 |  | Had to make validation checks include a check if input was an integer
7 | 2020-03-15 | Test checking | Construct | 1 | Integration test | 1 | 5 | 6 | Also had to add a check if input was a float
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75

## Time Log
Constants | [6 empty] | 0
Start date: | 36526 |  | AA |  | Grades: | AA | 1
End date: | 73051 |  | A |  |  | A | 0.95
Phases: | Analyze | 0 | Identifying customer needs |  | AB | 0.9 | 0 | 0
| Architect | 0 | High-level design |  | B | 0.85 | 0 | 0
| Plan project | 0 | Determine actions/effort for project duration |  | BC | 0.8 | 0 | 0
| Plan iteration | 0 | Determine actions/effort this iteration |  | C | 0.75 | 0 | 0
| Construct | 0 | Low-level design, coding, unit testing |  | CD | 0.7 | 43896 | 0
| Refactor | 0 | Restructure internal design |  | D | 0.65 | 43897 | 1
| Review | 0 | Examine test code for risk mitigation |  | F | 0.5 | 43898 | 2
| Integration test | 0 | End-to-end test of components to date |  |  |  | 43899 | 3
| Repattern | 0 | Restructure external design |  |  |  | 43900 | 4
| Postmortem | 0 | Capture post-development statistics |  |  |  | 43901 | 5
| Sandbox | 0 | Prove ideas, try concepts |  |  |  | 43902 | 6
Defect Types: | Requirements Change |  | NA |  | Iteration | NA | did not follow
| Requirements Clarification |  | 1 |  |  | 1 | very painful
| Product syntax |  | 2 |  |  | 2 | painful
| Product logic |  | 3 |  |  | 3 | neutral
| Product interface |  | 4 |  |  | 4 | helpful
| Product checking |  | 5 |  |  | 5 | very helpful
| Test syntax |  | 6 |  |  | 6
| Test logic |  | 7 |  |  | 7
| Test interface |  | 8 |  |  | 8
| Test checking |  | 9 |  |  | 9
| Bad Smell |  | 10 |  |  | 10 | 0
Y/N: | Yes |  | Passed |  |  | Passed | 0
| No |  | Passed with issues |  |  | Passed with issues | 0
Proxy Types: | - |  | Failed |  |  | Failed | Base
| Calculation |  | Not tested |  |  | Not tested | New
| Data |  | Not applicable |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS |  | L |  | M | L | VL
upper | -1.5 |  | 1.5 |  | 0.5 | 1.5 | 99999
mid | -2 |  | 1 |  | 0 | 1 | 2
lower | 0 |  | 0.5 |  | -0.5 | 0.5 | 1.5
| 0 |  | 0 |  | 0 | 0
<-- Mandatory
Time Recording Log
Use this worksheet to record the amount of time you spend on each activity. Use the "sandbox" activity to record time spent experimenting with the assignment requirements..
|  | Activity |  | Meaning
|  | Analyze |  | Identifying customer needs
|  | Architect |  | High-level design
|  | Plan project |  | Determine actions/effort for project duration
|  | Plan iteration |  | Determine actions/effort this iteration
|  | Construct |  | Low-level design, coding, unit testing
|  | Refactor |  | Restructure internal design
|  | Review |  | Examine test code for risk mitigation
|  | Integration test |  | End-to-end test of components to date
|  | Repattern |  | Restructure external design
|  | Postmortem |  | Capture post-development statistics
|  | Sandbox |  | Prove ideas, try concepts
| Start Time |  | Stop Time
Date | Hour | Min | Hour | Min | Interrupt | Delta | Activity | Iteration | Comments
2020-03-12 | 18 | 55 | 19 | 30 |  | 35 | Analyze | 1
2020-03-12 | 19 | 30 | 19 | 50 |  | 20 | Plan iteration | 1
2020-03-12 | 19 | 50 | 20 | 10 |  | 20 | Construct | 1
2020-03-13 | 15 | 15 | 17 | 55 |  | 160 | Construct | 1
2020-03-13 | 18 | 25 | 19 | 0 |  | 35 | Construct | 1
2020-03-13 | 19 | 10 | 19 | 30 |  | 20 | Sandbox | 1 | Had to figure out the hash function
2020-03-13 | 19 | 30 | 21 | 10 |  | 100 | Construct | 1
2020-03-14 | 16 | 0 | 16 | 20 |  | 20 | Review | 1
2020-03-14 | 16 | 25 | 18 | 45 | 15 | 125 | Integration test | 1
2020-03-15 | 15 | 10 | 16 | 10 |  | 60 | Integration test | 1
2020-03-15 | 17 | 10 | 18 | 0 |  | 50 | Integration test | 1
2020-03-15 | 18 | 0 | 18 | 10 |  | 10 | Postmortem | 1

## Lessons
Lessons Learned
Problems of Importance
1
2
3
4
5
Proposal for Improvements
1
2
3
4
5
Notes and Comments
1
2
3
4
5

## Coding Standard
Coding Standard
A coding standard provides a map so that the code generated by a group of programmers will be consistent and, therefore, easier to read and maintain.
File headings
Place a doc string at the beginning of each file. The doc string should state the purpose of the file's contents, the date the file was baselined, the date of any modifications subsequent to being baselined, and the name of the author. Each line of the doc string should be indented by four spaces. It can be delimited by either three double quotes or three single quotes. [Rationale: This provides identifying information for the file.]
Example
'''
Created on Aug 27, 2088
@author: David Umphress
'''
Use of docstrings elsewhere is optional. If used, they may be free form; i.e., this coding standard specifies no format.
Comments
Use # for comments other than doc strings. [Rationale: This style of commenting makes comments consistent across other programming languages.]
Example
# Return the answer to the universe
return 42
Do not include comments such as "#end if" to denote end of structural constructs. [Rationale: Indentation gives a visual cue to nesting; comments that indicate end of blocks of code decrease readability.]
Multiple assignment statements
Avoid multiple assignment statements. Use only in situations where readability would be significantly affected by using single assignment statements. [Rationale: Multiple logical lines per physical line result in an inaccurate LOC count.]
|  | Not OK | OK
|  | myVar1, myVar2 = 0, 1 | myVar1 = 0
myVar2 = 1
|  | import os, sys | import os
import sys
Spanning physical lines
Logical lines can span multiple physical lines (where a physical line is no more than 80 characters). In such cases, the continuation lines must be indented one indentation beyond the initial line. Break lines after operators or commas. [Rationale: Indentation improves readability.]
Do not span strings over more than one physical line. In cases where a string won’t fit on a physical line, break the string into individual parts that will fit on a line and concatenate the parts. [Rationale: This simplifies construction of tools that count lines of code.]
|  | Not OK | OK
|  | myVar1 = myVar2 + myVar3 + \ | myVar1 = myVar2 + myVar3 + \
|  | myVar4 | myVar4
|  | myString = '''multi-line | myString='multi-line ’ + \
|  | string''' | ‘string’
Blank lines
Use blank lines to break up related chunks of code. Use at least one blank line between all methods. [Rationale: Blank lines visually segment blocks of related code, thus making it more understandable.]
Code readability
Code should be as self-documenting as possible. For example:
· Identifiers should be given meaningful names that indicate purpose or use.
· Single letters should only be used as names for loop indices when mirroring a mathematical equation specified in the requirements, otherwise, loop indices should be given names that indicate their use.
· Magic numbers – meaning, numbers that appear without explanation in source code – are to be avoided. If they appear, they should be assigned to identifiers that describe their purpose.
· Comments should be used sparingly as an aid to understanding non-intuitive code structure, complex calculations, unique circumstances, etc. It should not be a substitute for unreadable code.
[Rationale: These practices improve comprehension of code.]
Identifier naming
Variables should follow a camel-case convention (i.e., the identifier consists of a series of words with the spaces removed; the beginning letter should be lower case; the beginning letter of each word should be uppercase.)
Class names should be nouns in camel-case, with the first letter capitalized.
Example
class MyClass
Function names and method names should be in camel-case, with the first letter in lower case. The name should connote action and thus should be a verb or verb phrase.
Example
def run()
def getValue()
Methods that retrieve a Boolean object state must use the prefix is in the method name.
Example
isEnabled()
Identifiers designated to be constant should be nouns in all upper case with words separated by an underscore. All other identifiers should be nouns in camel-case, with the first letter in lower case.
Multiple inheritance
Do not use multiple inheritance. [Rationale: This practice decreases understandability.]
File contents
Unless specified otherwise, each class should be stored in its own file. The name of the file should be the name of the class followed by a “.py” extension. For example, class “MyComponent” should be located in a file named “MyComponent.py”.
Test code should be placed in a file whose file name clearly reflects what component is being tested. In most cases, the file name will be the component name appended with “Test.py”. For example, “MyComponentTest.py” would contain the code that tests “MyComponent.py”.
File structure
Code should be developed in your IDE using the following general directory/file structure:

## Counting Standard
Counting Standard
A counting standard defines how to determine the number of lines of code.
Each non-blank, non-comment, non-doc string line of production code counts as one line of code. Do not count test code.
Example:
| ''' | doc string … not a line of code
| Created to demonstrate the counting standard | doc string … not a line of code
| Baselined: 1 Aug 2099 | doc string … not a line of code
| Modified: 29 Sep 2099 | doc string … not a line of code
| @author: D. Umphress | doc string … not a line of code
| ''' | doc string … not a line of code
| import something | line of code
blank line … not a line of code
| def fib(n): | line of code
| ''' fib(n) calculates the Fibbanacci value of n ''' | doc string … not a line of code
| prev = 0 | line of code
| next = 1 | line of code
blank line … not a line of code
| for i in range(n - 1): | line of code
| temp = next | line of code
| next = next + prev | line of code
| prev = temp | line of code
| return next | line of code
total lines of code in the file: 9
total number of components: 1
name: fib
component method count = 1
component LOC count= 8

## Source (hidden)
Source Code
Paste production source code here. (1) copy your code to the clipboard, (2) click on the "PASTE ME" cell (not the entire row), (3) paste. Do not paste test code.
PASTE ME

## Constants (hidden)
Constants | [5 empty] | 0
Start date: | 2000-01-01 |  |  | Grades: | AA | 100% |  |  | 2020-03-15
End date: | 2100-01-01 |  |  |  | A | 95%
Phases: | Analyze |  | Identifying customer needs |  | AB | 90%
| Architect |  | High-level design |  | B | 85%
| Plan project |  | Determine actions/effort for project duration |  | BC | 80%
| Plan iteration |  | Determine actions/effort this iteration |  | C | 75%
| Construct |  | Low-level design, coding, unit testing |  | CD | 70% | 2020-03-06 | 0 | 0 | AM
| Refactor |  | Restructure internal design |  | D | 65% | 2020-03-07 | 1 | 5 | PM
| Review |  | Examine test code for risk mitigation |  | F | 50% | 2020-03-08 | 2 | 10
| Integration test |  | End-to-end test of components to date |  |  |  | 2020-03-09 | 3 | 15
| Repattern |  | Restructure external design |  |  |  | 2020-03-10 | 4 | 20
| Postmortem |  | Capture post-development statistics |  |  |  | 2020-03-11 | 5 | 25
| Sandbox |  | Prove ideas, try concepts |  |  |  | 2020-03-12 | 6 | 30
[7 empty] | 2020-03-13 | 7 | 35
[7 empty] | 2020-03-14 | 8 | 40
[7 empty] | 2020-03-15 | 9 | 45
[7 empty] | 2020-03-16 | 10 | 50
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow |  | 2020-03-17 | 11 | 55
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful |  | 2020-03-18 | 12
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful |  | 2020-03-19 | 13
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral |  | 2020-03-20 | 14
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful |  | 2020-03-21 | 15
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful |  | 2020-03-22 | 16
| Test syntax | Syntax flaws in the test code |  | 6 |  |  | 2020-03-23 | 17
| Test logic | Logic flaws in the test code |  | 7 |  |  | 2020-03-24 | 18
| Test interface | Flaws in the interface of a component of the test code |  | 8 |  |  | 2020-03-25 | 19
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9 |  |  | 2020-03-26 | 20
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 |  |  | 2020-03-27 | 21
Y/N: | Yes |  |  | Passed |  |  | 2020-03-28 | 22
| No |  |  | Passed with issues |  |  | 2020-03-29 | 23
Proxy Types: | - |  |  | Failed | Base |  | 2020-03-30
| Calculation |  |  | Not tested | New |  | 2020-03-31
| Data |  |  | Not applicable | Reusable |  | 2020-04-01
| I/O | [5 empty] | 2020-04-02
| Logic | [5 empty] | 2020-04-03
2020-04-04
Sizes: | VS | S | M | L | VL | VS
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999 | S
mid | -2 | -1 | 0 | 1 | 2 | M
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5 | L
VL
<-- Mandatory |  | ✔