## Description
COMP 6700/6706 -- Software Process
Assignment: | CA05
5700/6700 due date: | 2012-11-04 | 11:55pm | Central time | Blackout begins | 2012-11-01 | 6pm
6706 due date: | 2012-11-11 | 11:55pm | Central time | Blackout begins | 2012-11-07 | 6pm
Name of this file: | CA05.xls
Objective: | to gain experience with estimating size and effort.
Assignment: | The worksheets in this assignment provide you with a hypothetical historical development database as well as with a forecast of standard components for a hypothetical project. Please use this information to determine the size and effort of the project.
Notes: | - This homework assignment is be accomplished individually
Deliverables: | - This spreadsheet with "Assignment" completed.
- (Optional) Explanatory calculations on worksheets "Calc-1", "Calc-2", etc.
- When complete, upload the spreadsheet to Canvas
Special Instructions: | - Selected cells in this spreadsheet are locked against inadvertent editing. Should you need to unlock the spreadsheet, select the protected worksheet, select Tools -> Protection -> unprotect. Use "comp6700" if a password is requested.

## Process
Process Script
Entry |  | - this spreadsheet
Tasks |  | see lecture notes
Exit |  | - complete "Assignment" worksheet
- (optional) intermediate calculations
Quality checks
General
Are all regions highlighted in yellow complete? (Either with a value, or NA if the cell is not applicable. No units of measure.)
Are supporting calculations understandable?
Size matrix
Are buckets sized by a log-normal distribution?
Component sizing
Has each new component been given a relative size?
Are new components sized according to the size matrix?
Are base components accounted for?
Size calculations
Is effort based on the new and modified components?
Is productivity calcuated in LOC/hr?
Are correlation values based on correct data sets?
Is the range calculation valid? It is correct?
Does the Lower Prediction Interval (LPI) represent a valid value?
Top-down effort calculations
Are the lifecycle activities distributed according to historical performance?
Useful Excel Functions
| correl | parms: | x's, y's
|  | returns: | correlation coefficient
|  | example: | given the data at right, | X | Y
|  |  | "=CORREL(F83:F88,G83:G88)" | 1 | 2
|  |  | yields | 2 | 4
|  |  | 0.98372 | 4 | 8
|  |  |  | 5 | 10
|  |  |  | 6 | 12
|  |  |  | 7 | 17
| average | parms: | values
|  | returns: | average of the values
|  | example: | the average of the x's above is "=AVERAGE(F42:F47)", or |  |  | 4.1667
| stdev | parms: | values
|  | returns: | standard deviation of the values
|  | example: | the std of the x's above is "=STDEV(F42:F47)", or |  |  | 2.3166
| sum | parms: | values
|  | returns: | sum of the values
|  | example: | the sum of the x's above is "=SUM(F42:F47)", which yields |  |  | 25
| ln | parms: | value
|  | returns: | natural logarithm of the value
|  | example: | the natural logarithm of the value above is "=ln(I59)", which yields |  |  | 3.2189
| exp | parms: | power
|  | returns: | 2.718^power
|  | example: | the antilog of the natural log abve "=exp(I59)", which is |  |  | 25
| ceiling | parms: | value, places
|  | returns: | a value that is rounded up to the nearest significant digit
|  | example: | the integer ceiling of 4.1667 is "=ceiling(4.1667,1)", which is: |  |  | 5
| floor | parms: | value, places
|  | returns: | a value that is rounded down to the nearest significant digit
|  | example: | the integer floor of 4.1667 is "=floor(4.1667,1)", which is |  |  | 4

## Component History
Component History: The following is a record of historical components.
| Identifier | Total Loc | Methods | Type
| Component1 | 14 | 1 | Calculation
| Component2 | 152 | 14 | Calculation
| Component3 | 71 | 7 | Data
| Component4 | 341 | 26 | I/O
| Component5 | 19 | 1 | Calculation
| Component6 | 38 | 1 | Logic
| Component7 | 56 | 6 | I/O
| Component8 | 16 | 1 | Data
| Component9 | 224 | 17 | I/O
| Component10 | 296 | 24 | Logic
| Component11 | 225 | 16 | I/O
| Component12 | 82 | 4 | I/O
| Component13 | 28 | 2 | I/O
| Component14 | 19 | 2 | Calculation
| Component15 | 112 | 7 | Logic
| Component16 | 16 | 1 | Data
| Component17 | 235 | 19 | Data
| Component18 | 129 | 10 | Data
| Component19 | 83 | 8 | Data
| Component20 | 104 | 9 | Logic
| Component21 | 139 | 12 | Logic
| Component22 | 77 | 3 | Logic
| Component23 | 23 | 2 | Logic
| Component24 | 209 | 17 | I/O
| Component25 | 33 | 3 | Data
| Component26 | 89 | 5 | I/O
| Component27 | 167 | 13 | I/O
| Component28 | 119 | 11 | Logic
| Component29 | 104 | 7 | Data
| Component30 | 15 | 3 | Data
| Component31 | 42 | 3 | Data
| Component32 | 126 | 11 | Calculation
| Component33 | 117 | 7 | Logic
| Component34 | 106 | 8 | Calculation
| Component35 | 140 | 13 | Calculation
| Component36 | 9 | 1 | Calculation
| Component37 | 194 | 15 | Data
| Component38 | 55 | 8 | Logic
| Component39 | 68 | 3 | Logic
| Component40 | 308 | 24 | Calculation
| Component41 | 124 | 5 | Data
| Component42 | 5 | 1 | I/O
| Component43 | 181 | 17 | Data
| Component44 | 119 | 9 | Logic
| Component45 | 247 | 20 | I/O
| Component46 | 66 | 5 | I/O
| Component47 | 38 | 2 | Calculation
| Component48 | 125 | 8 | I/O
| Component49 | 12 | 2 | Logic
| Component50 | 65 | 5 | Calculation
| Component51 | 141 | 12 | Data
| Component52 | 47 | 1 | Calculation
| Component53 | 72 | 5 | Calculation
| Component54 | 60 | 4 | I/O
| Component55 | 102 | 10 | Calculation
| Component56 | 112 | 9 | Data
| Component57 | 168 | 14 | Data
| Component58 | 25 | 5 | Logic
| Component59 | 164 | 11 | I/O
| Component60 | 37 | 2 | I/O
| Component61 | 57 | 4 | Data
| Component62 | 17 | 1 | Calculation
| Component63 | 176 | 12 | Data
| Component64 | 223 | 18 | Calculation
| Component65 | 26 | 1 | Data
| Component66 | 51 | 6 | I/O
| Component67 | 170 | 14 | Logic
| Component68 | 268 | 18 | Data
| Component69 | 222 | 17 | Logic
| Component70 | 62 | 6 | Calculation
| Component71 | 83 | 7 | Calculation
| Component72 | 219 | 21 | Data
| Component73 | 115 | 10 | Logic
| Component74 | 29 | 4 | Calculation
| Component75 | 108 | 11 | Logic
| Component76 | 152 | 13 | Logic
| Component77 | 52 | 3 | Data
| Component78 | 5 | 1 | Calculation
| Component79 | 196 | 16 | Logic
| Component80 | 82 | 7 | Data
| Component81 | 142 | 11 | Logic
| Component82 | 10 | 2 | Data
| Component83 | 33 | 2 | I/O
| Component84 | 52 | 3 | Logic
| Component85 | 20 | 4 | Logic
| Component86 | 94 | 11 | Calculation
| Component87 | 55 | 0 | Data

## Project History
Project History: The following is a record of actual/estimated performance on past projects. Note: times are in minutes.
| Identifier | Raw LOC (LOCr) | Planned LOC (LOCp) | Actual LOC (LOCa) | Planned Effort (Ep) | Actual Effort (Ea)
| Project1 | 579 | 476 | 647 | 2517 | 2400
| Project2 | 760 | 1138 | 2191 | 2036 | 6139
| Project3 | 369 | 572 | 1186 | 987 | 3564
| Project4 | 397 | 186 | 308 | 1847 | 812
| Project5 | 410 | 808 | 1574 | 3188 | 7486
| Project6 | 1159 | 904 | 1401 | 2988 | 5063
| Project7 | 1534 | 1880 | 3084 | 2904 | 9448
| Project8 | 1884 | 4117 | 8241 | 4810 | 40009
| Project9 | 2357 | 1676 | 2916 | 7593 | 12262
| Project10 | 540 | 643 | 1476 | 2707 | 4321
| Project11 | 1624 | 2254 | 3987 | 3394 | 14047
| Project12 | 1388 | 1658 | 2807 | 7771 | 6884
| Project13 | 1226 | 1816 | 3961 | 4648 | 13927
| Project14 | 526 | 533 | 857 | 1722 | 2376
| Project15 | 1004 | 1492 | 2845 | 3415 | 10562
| Project16 | 859 | 672 | 1331 | 2589 | 4482
| Project17 | 3293 | 2114 | 2915 | 8558 | 9045
| Project18 | 1061 | 1177 | 2769 | 3109 | 7030
| Project19 | 2134 | 2670 | 4551 | 6662 | 11951
| Project20 | 2612 | 2666 | 5138 | 5218 | 15292

## Activities
Activities: The following describes the to-date percentages for development time and defects.
| Phase | Time in Phase To Date % | Defects Injected To Date % | Defects Removed To Date %
| Analysis | 13% | 5% | 0%
| Architecture | 10% | 10% | 0%
| Project planning | 1% | 0% | 0%
| Interation Planning | 5% | 0% | 0%
| Construction | 50% | 77% | 30%
| Refactoring | 4% | 3% | 1%
| Review | 1% | 0% | 3%
| Integration Test | 8% | 0% | 66%
| Repatterning | 1% | 0% | 0%
| Postmortem | 3% | 0% | 0%
| Sandbox | 4% | 5% | 0%
| Total | 100% | 100% | 100%

## Architecture
Architecture: The following CRC cards describe the solution.
| Component Name | ForecastedComponent01
| Design Approach | OO
Superclass
| Component Type | Data
| Collaborators | ForecastedComponent02, ForecastedComponent05
| Operations | 5 methods
| Notes | No historical component approximates the functionality of this component. This component is most similar in complexity to Component51
| Component Name | ForecastedComponent02
| Design Approach | OO
| Superclass | ForecastedComponent06
| Component Type | Data
| Collaborators | ForecastedComponent03, ForecastedComponent04
| Operations | 7 methods
| Notes | The functionality of this component is available by deleting 17 LOC from, modifying 16 LOC of, and adding 29 LOC to Component82 as well as adding 1 new method(s) to Component82
| Component Name | ForecastedComponent03
| Design Approach | OO
Superclass
| Component Type | Logic
Collaborators
| Operations | 5 methods
| Notes | The functionality of this component is available by deleting 14 LOC from, modifying 13 LOC of, and adding 21 LOC to Component70 as well as adding 1 new method(s) to Component70
| Component Name | ForecastedComponent04
| Design Approach | OO
Superclass
| Component Type | Logic
Collaborators
| Operations | 4 methods
| Notes | No historical component approximates the functionality of this component. This component is most similar in complexity to Component31
| Component Name | ForecastedComponent05
| Design Approach | FD
Superclass
| Component Type | I/O
Collaborators
| Operations | 1 method
| Notes | The functionality of this component is available by deleting 12 LOC from, modifying 11 LOC of, and adding 20 LOC to Component59.
| Component Name | ForecastedComponent06
| Design Approach | OO
Superclass
| Component Type | Logic
Collaborators
| Operations | 5 methods
| Notes | No historical component approximates the functionality of this component. This component is most similar in complexity to Component58

## COCOMO
COCOMO: The following values are COCOMO reference factors and drivers
|  | Very Low | Low | Nominal | High | Very High | Extra High
Scale Factors
| Precedent | 6.2 | 4.96 | 3.72 | 2.48 | 1.24 | 0
| Flexibility | 5.07 | 4.05 | 3.04 | 2.03 | 1.01 | 0
| Risk resolution | 7.07 | 5.65 | 4.24 | 2.83 | 1.41 | 0
| Team Cohesion | 5.48 | 4.38 | 3.29 | 2.19 | 1.1 | 0
| Process Level | 7.8 | 6.24 | 4.68 | 3.12 | 1.56 | 0
Cost Drivers
Product attributes
| Required software reliability | 0.82 | 0.92 | 1 | 1.1 | 1.26 | 1.26
| Size of application database | 0.94 | 0.94 | 1 | 1.08 | 1.16 | 1.16
| Complexity of the product | 0.7 | 0.85 | 1 | 1.15 | 1.3 | 1.65
Hardware attributes
| Run-time performance constraints | 1 | 1 | 1 | 1.11 | 1.3 | 1.66
| Memory constraints | 1 | 1 | 1 | 1.06 | 1.21 | 1.56
| Volatility of the virtual machine environment | 0.87 | 0.87 | 1 | 1.15 | 1.3 | 1.3
| Required turnabout time | 0.87 | 0.87 | 1 | 1.07 | 1.15 | 1.15
Personnel attributes
| Analyst capability | 1.42 | 1.19 | 1 | 0.85 | 0.71 | 0.71
| Applications experience | 1.22 | 1.1 | 1 | 0.88 | 0.81 | 0.81
| Software engineer capability | 1.34 | 1.15 | 1 | 0.88 | 0.76 | 0.76
| Virtual machine experience | 1.21 | 1.1 | 1 | 0.9 | 0.9 | 0.9
| Programming language experience | 1.14 | 1.07 | 1 | 0.95 | 0.95 | 0.95
| Personnel continuity | 1.29 | 1.1 | 1 | 0.88 | 0.81 | 0.81
Project attributes
| Application of software engineering methods | 1.24 | 1.1 | 1 | 0.91 | 0.82 | 0.82
| Use of software tools | 1.24 | 1.1 | 1 | 0.91 | 0.83 | 0.83
| Required development schedule | 1.23 | 1.08 | 1 | 1.04 | 1.1 | 1.1

## Solution
Name: | Haden Stuart
Username: | has0027
Instructor Assessment
Aspect | Possible Score | Earned Score | Comment
Size matrix | 10
Component sizing | 10
Size calculations | 10
Bottom-up effort calculations | 10
Top-down effort calculations | 10
Total | 50 | 0
Estimates on New Development: Please provide answers to the questions below. If a result is not calculable, please fill the box with a "NA" and defend your answer in the supporting calculations section. Each cell should contain a number, "NA", or a value from a drop-down menu; do not indicate units (such as "min", "hr", "LOC", etc.) Please do not leave any boxes blank; I will assume that an empty box means you did not answer the question.
Parameters
normal | Day 1
log-normal | Day 2
not applicable | Day 3
LOCE x Time | Day 4
LOCA x Time | Day 5
Productivity | Day 6
not applicable | Day 7
VS | Day 8
S | Day 9
M | Day 10
L | Day 11
VL | Day 12
not applicable | Day 13
Calculation | Day 14
Data | Day 15
IO | Day 16
Logic | Day 17
not applicable | Day 18
low | Day 19
medium | Day 20
high | Day 21
Decision D | Day 22
not applicable | Day 23
Day 24
Day 25
Day 26
Day 27
Day 28
Day 29
Day 30
Day 31
Never
Solution
Size matrix
| Low | Mid | High
VS | 1 | 6 | 7 | LOC/Method
S | 7 | 8 | 10 | LOC/Method
M | 10 | 13 | 15 | LOC/Method
L | 15 | 19 | 23 | LOC/Method
VL | 23 | 28 | Big | LOC/Method
Component sizing
Component | Raw New LOC
ForecastedComponent01 | 65 | LOC
ForecastedComponent02 | 93 | LOC
ForecastedComponent03 | 112 | LOC
ForecastedComponent04 | 52 | LOC
ForecastedComponent05 | 44 | LOC
ForecastedComponent06 | 30 | LOC
Size calculations
Total raw size (LOCr) | 396 | LOC
Planned size (LOCp) | 835 | LOC
Lower prediction interval (LPI) | 307 | LOC
Upper prediction interval (UPI) | 1733 | LOC
Confidence | low
Bottom-up effort calculations
Productivity (Prod) | 17 | LOC/hr
Planned effort (Ep) | 2883 | Minutes
Lower prediction interval (LPI) | 1670 | Minutes
Upper prediction interval (UPI) | 4175 | Minutes
Confidence | high
How much overall effort do you anticipate expending in construction? | 1442 | Minutes
Top-down effort calculations
Person months, if all factors are nominal: | 2.4 | Person Months
Person months, worst case: | 7.5 | Person Months
Person months, best case: | 2.1 | Person Months

## Calc-1
Supporting Calculations for
Size matrix
| Low | Mid | High |  | Identifier | Total Loc | Methods | Type | Loc/Methods | ln(Loc/Methods) | Relative Size
VS | 1 | 5.5707 | 6.8192 | LOC/Method | Component1 | 14 | 1 | Calculation | 14 | 2.6391 | M
S | 6.8192 | 8.3475 | 10.2184 | LOC/Method | Component2 | 152 | 14 | Calculation | 10.8571 | 2.3848 | M
M | 10.2184 | 12.5085 | 15.3119 | LOC/Method | Component3 | 71 | 7 | Data | 10.1429 | 2.3168 | S
L | 15.3119 | 18.7436 | 22.9444 | LOC/Method | Component4 | 341 | 26 | I/O | 13.1154 | 2.5738 | M
VL | 22.9444 | 28.0867 | Big | LOC/Method | Component5 | 19 | 1 | Calculation | 19 | 2.9444 | L
[5 empty] | Component6 | 38 | 1 | Logic | 38 | 3.6376 | VL
[5 empty] | Component7 | 56 | 6 | I/O | 9.3333 | 2.2336 | S
[5 empty] | Component8 | 16 | 1 | Data | 16 | 2.7726 | L
average = | 2.5264 |  |  |  | Component9 | 224 | 17 | I/O | 13.1765 | 2.5784 | M
std = | 0.40444 |  |  |  | Component10 | 296 | 24 | Logic | 12.3333 | 2.5123 | M
[5 empty] | Component11 | 225 | 16 | I/O | 14.0625 | 2.6435 | M
[5 empty] | Component12 | 82 | 4 | I/O | 20.5 | 3.0204 | L
[5 empty] | Component13 | 28 | 2 | I/O | 14 | 2.6391 | M
[5 empty] | Component14 | 19 | 2 | Calculation | 9.5 | 2.2513 | S
[5 empty] | Component15 | 112 | 7 | Logic | 16 | 2.7726 | L
[5 empty] | Component16 | 16 | 1 | Data | 16 | 2.7726 | L
[5 empty] | Component17 | 235 | 19 | Data | 12.3684 | 2.5151 | M
[5 empty] | Component18 | 129 | 10 | Data | 12.9 | 2.5572 | M
[5 empty] | Component19 | 83 | 8 | Data | 10.375 | 2.3394 | M
[5 empty] | Component20 | 104 | 9 | Logic | 11.5556 | 2.4472 | M
[5 empty] | Component21 | 139 | 12 | Logic | 11.5833 | 2.4496 | M
[5 empty] | Component22 | 77 | 3 | Logic | 25.6667 | 3.2452 | VL
[5 empty] | Component23 | 23 | 2 | Logic | 11.5 | 2.4423 | M
[5 empty] | Component24 | 209 | 17 | I/O | 12.2941 | 2.5091 | M
[5 empty] | Component25 | 33 | 3 | Data | 11 | 2.3979 | M
[5 empty] | Component26 | 89 | 5 | I/O | 17.8 | 2.8792 | L
[5 empty] | Component27 | 167 | 13 | I/O | 12.8462 | 2.553 | M
[5 empty] | Component28 | 119 | 11 | Logic | 10.8182 | 2.3812 | M
[5 empty] | Component29 | 104 | 7 | Data | 14.8571 | 2.6985 | M
[5 empty] | Component30 | 15 | 3 | Data | 5 | 1.6094 | VS
[5 empty] | Component31 | 42 | 3 | Data | 14 | 2.6391 | M
[5 empty] | Component32 | 126 | 11 | Calculation | 11.4545 | 2.4384 | M
[5 empty] | Component33 | 117 | 7 | Logic | 16.7143 | 2.8163 | L
[5 empty] | Component34 | 106 | 8 | Calculation | 13.25 | 2.584 | M
[5 empty] | Component35 | 140 | 13 | Calculation | 10.7692 | 2.3767 | M
[5 empty] | Component36 | 9 | 1 | Calculation | 9 | 2.1972 | S
[5 empty] | Component37 | 194 | 15 | Data | 12.9333 | 2.5598 | M
[5 empty] | Component38 | 55 | 8 | Logic | 6.875 | 1.9279 | S
[5 empty] | Component39 | 68 | 3 | Logic | 22.6667 | 3.1209 | L
[5 empty] | Component40 | 308 | 24 | Calculation | 12.8333 | 2.552 | M
[5 empty] | Component41 | 124 | 5 | Data | 24.8 | 3.2108 | VL
[5 empty] | Component42 | 5 | 1 | I/O | 5 | 1.6094 | VS
[5 empty] | Component43 | 181 | 17 | Data | 10.6471 | 2.3653 | M
[5 empty] | Component44 | 119 | 9 | Logic | 13.2222 | 2.5819 | M
[5 empty] | Component45 | 247 | 20 | I/O | 12.35 | 2.5137 | M
[5 empty] | Component46 | 66 | 5 | I/O | 13.2 | 2.5802 | M
[5 empty] | Component47 | 38 | 2 | Calculation | 19 | 2.9444 | L
[5 empty] | Component48 | 125 | 8 | I/O | 15.625 | 2.7489 | L
[5 empty] | Component49 | 12 | 2 | Logic | 6 | 1.7918 | VS
[5 empty] | Component50 | 65 | 5 | Calculation | 13 | 2.5649 | M
[5 empty] | Component51 | 141 | 12 | Data | 11.75 | 2.4639 | M
[5 empty] | Component52 | 47 | 1 | Calculation | 47 | 3.8501 | VL
[5 empty] | Component53 | 72 | 5 | Calculation | 14.4 | 2.6672 | M
[5 empty] | Component54 | 60 | 4 | I/O | 15 | 2.7081 | M
[5 empty] | Component55 | 102 | 10 | Calculation | 10.2 | 2.3224 | S
[5 empty] | Component56 | 112 | 9 | Data | 12.4444 | 2.5213 | M
[5 empty] | Component57 | 168 | 14 | Data | 12 | 2.4849 | M
[5 empty] | Component58 | 25 | 5 | Logic | 5 | 1.6094 | VS
[5 empty] | Component59 | 164 | 11 | I/O | 14.9091 | 2.702 | M
[5 empty] | Component60 | 37 | 2 | I/O | 18.5 | 2.9178 | L
[5 empty] | Component61 | 57 | 4 | Data | 14.25 | 2.6568 | M
[5 empty] | Component62 | 17 | 1 | Calculation | 17 | 2.8332 | L
[5 empty] | Component63 | 176 | 12 | Data | 14.6667 | 2.6856 | M
[5 empty] | Component64 | 223 | 18 | Calculation | 12.3889 | 2.5168 | M
[5 empty] | Component65 | 26 | 1 | Data | 26 | 3.2581 | VL
[5 empty] | Component66 | 51 | 6 | I/O | 8.5 | 2.1401 | S
[5 empty] | Component67 | 170 | 14 | Logic | 12.1429 | 2.4967 | M
[5 empty] | Component68 | 268 | 18 | Data | 14.8889 | 2.7006 | M
[5 empty] | Component69 | 222 | 17 | Logic | 13.0588 | 2.5695 | M
[5 empty] | Component70 | 62 | 6 | Calculation | 10.3333 | 2.3354 | M
[5 empty] | Component71 | 83 | 7 | Calculation | 11.8571 | 2.4729 | M
[5 empty] | Component72 | 219 | 21 | Data | 10.4286 | 2.3445 | M
[5 empty] | Component73 | 115 | 10 | Logic | 11.5 | 2.4423 | M
[5 empty] | Component74 | 29 | 4 | Calculation | 7.25 | 1.981 | S
[5 empty] | Component75 | 108 | 11 | Logic | 9.8182 | 2.2842 | S
[5 empty] | Component76 | 152 | 13 | Logic | 11.6923 | 2.4589 | M
[5 empty] | Component77 | 52 | 3 | Data | 17.3333 | 2.8526 | L
[5 empty] | Component78 | 5 | 1 | Calculation | 5 | 1.6094 | VS
[5 empty] | Component79 | 196 | 16 | Logic | 12.25 | 2.5055 | M
[5 empty] | Component80 | 82 | 7 | Data | 11.7143 | 2.4608 | M
[5 empty] | Component81 | 142 | 11 | Logic | 12.9091 | 2.5579 | M
[5 empty] | Component82 | 10 | 2 | Data | 5 | 1.6094 | VS
[5 empty] | Component83 | 33 | 2 | I/O | 16.5 | 2.8034 | L
[5 empty] | Component84 | 52 | 3 | Logic | 17.3333 | 2.8526 | L
[5 empty] | Component85 | 20 | 4 | Logic | 5 | 1.6094 | VS
[5 empty] | Component86 | 94 | 11 | Calculation | 8.5455 | 2.1454 | S
[5 empty] | Component87 | 55 | 0 | Data

## Calc-2
Supporting Calculations for
Component sizing
| Architecture | Estimation Basis | Relative Size | Modified LOC | Added LOC | Deleted LOC | Base LOC | New Methods | LOC/Method | New LOC | Totals
| ForecastedComponent01 | Component 51 | M | 0 | 0 | 0 | 0 | 5 | 13 | 65 | 65
| ForecastedComponent02 | Component 82 | VS | 16 | 29 | 17 | 45 | 8 | 6 | 48 | 93 | For new methods I did, operations + new methods = 7 + 1 = 8
| ForecastedComponent03 | Component 70 | M | 13 | 21 | 14 | 34 | 6 | 13 | 78 | 112 | For new methods I did, operations + new methods = 5 + 1 = 6
| ForecastedComponent04 | Component 31 | M | 0 | 0 | 0 | 0 | 4 | 13 | 52 | 52
| ForecastedComponent05 | Component 59 | M | 11 | 20 | 12 | 31 | 1 | 13 | 13 | 44
| ForecastedComponent06 | Component 58 | VS | 0 | 0 | 0 | 0 | 5 | 6 | 30 | 30
[10 empty] | LOCr = | 396
| Component | Raw New LOC
| ForecastedComponent01 | 65 | LOC
| ForecastedComponent02 | 93 | LOC
| ForecastedComponent03 | 112 | LOC
| ForecastedComponent04 | 52 | LOC
| ForecastedComponent05 | 44 | LOC
| ForecastedComponent06 | 30 | LOC

## Calc-3
Supporting calculations for
Size calculations
| Identifier | Raw LOC (LOCr) | Planned LOC (LOCp) | Actual LOC (LOCa) | Planned Effort (Ep) | Actual Effort (Ea) | LOCa/LOCr | Size Calculations
| Project1 | 579 | 476 | 647 | 2517 | 2400 | 1.1174 | LOCr = | 396
| Project2 | 760 | 1138 | 2191 | 2036 | 6139 | 2.8829 | sum(LOCa)/sum(LOCr) = | 2.1071
| Project3 | 369 | 572 | 1186 | 987 | 3564 | 3.2141 | LOCp = | 835
| Project4 | 397 | 186 | 308 | 1847 | 812 | 0.77582 | LPI = | 307
| Project5 | 410 | 808 | 1574 | 3188 | 7486 | 3.839 | UPI = | 1733
| Project6 | 1159 | 904 | 1401 | 2988 | 5063 | 1.2088 | Confidence = | 0.40388 | LOW
| Project7 | 1534 | 1880 | 3084 | 2904 | 9448 | 2.0104
| Project8 | 1884 | 4117 | 8241 | 4810 | 40009 | 4.3742
| Project9 | 2357 | 1676 | 2916 | 7593 | 12262 | 1.2372
| Project10 | 540 | 643 | 1476 | 2707 | 4321 | 2.7333
| Project11 | 1624 | 2254 | 3987 | 3394 | 14047 | 2.455
| Project12 | 1388 | 1658 | 2807 | 7771 | 6884 | 2.0223 | Total raw size (LOCr) | 396 | LOC
| Project13 | 1226 | 1816 | 3961 | 4648 | 13927 | 3.2308 | Planned size (LOCp) | 835 | LOC
| Project14 | 526 | 533 | 857 | 1722 | 2376 | 1.6293 | Lower prediction interval (LPI) | 307 | LOC
| Project15 | 1004 | 1492 | 2845 | 3415 | 10562 | 2.8337 | Upper prediction interval (UPI) | 1733 | LOC
| Project16 | 859 | 672 | 1331 | 2589 | 4482 | 1.5495 | Confidence | LOW
| Project17 | 3293 | 2114 | 2915 | 8558 | 9045 | 0.88521
| Project18 | 1061 | 1177 | 2769 | 3109 | 7030 | 2.6098
| Project19 | 2134 | 2670 | 4551 | 6662 | 11951 | 2.1326
| Project20 | 2612 | 2666 | 5138 | 5218 | 15292 | 1.9671
[6 empty] | min = | 0.77582
[6 empty] | max = | 4.3742

## Calc-4
Supporting Calculations for
Bottom-up effort calculations
| Identifier | Raw LOC (LOCr) | Planned LOC (LOCp) | Actual LOC (LOCa) | Planned Effort (Ep) | Actual Effort (Ea) | LOCa/LOCr | Ea/LOCa | Size Calculations
| Project1 | 579 | 476 | 647 | 2517 | 2400 | 1.1174 | 3.7094 | LOCr = | 396
| Project2 | 760 | 1138 | 2191 | 2036 | 6139 | 2.8829 | 2.8019 | sum(LOCa)/sum(LOCr) = | 2.1071
| Project3 | 369 | 572 | 1186 | 987 | 3564 | 3.2141 | 3.0051 | LOCp = | 835
| Project4 | 397 | 186 | 308 | 1847 | 812 | 0.77582 | 2.6364 | LPI = | 307
| Project5 | 410 | 808 | 1574 | 3188 | 7486 | 3.839 | 4.756 | UPI = | 1733
| Project6 | 1159 | 904 | 1401 | 2988 | 5063 | 1.2088 | 3.6138 | Confidence = | 0.40388 | LOW
| Project7 | 1534 | 1880 | 3084 | 2904 | 9448 | 2.0104 | 3.0636
| Project8 | 1884 | 4117 | 8241 | 4810 | 40009 | 4.3742 | 4.8549
| Project9 | 2357 | 1676 | 2916 | 7593 | 12262 | 1.2372 | 4.2051
| Project10 | 540 | 643 | 1476 | 2707 | 4321 | 2.7333 | 2.9275 | Effort Calculations
| Project11 | 1624 | 2254 | 3987 | 3394 | 14047 | 2.455 | 3.5232 | Prod = | 17.3763
| Project12 | 1388 | 1658 | 2807 | 7771 | 6884 | 2.0223 | 2.4524 | sum(Ea)/sum(LOCa) = | 3.453
| Project13 | 1226 | 1816 | 3961 | 4648 | 13927 | 3.2308 | 3.516 | Ep = | 2883.2426
| Project14 | 526 | 533 | 857 | 1722 | 2376 | 1.6293 | 2.7725 | LPI = | 1670
| Project15 | 1004 | 1492 | 2845 | 3415 | 10562 | 2.8337 | 3.7125 | UPI = | 4175
| Project16 | 859 | 672 | 1331 | 2589 | 4482 | 1.5495 | 3.3674 | Confidence = | 0.89364 | HIGH
| Project17 | 3293 | 2114 | 2915 | 8558 | 9045 | 0.88521 | 3.1029
| Project18 | 1061 | 1177 | 2769 | 3109 | 7030 | 2.6098 | 2.5388
| Project19 | 2134 | 2670 | 4551 | 6662 | 11951 | 2.1326 | 2.626
| Project20 | 2612 | 2666 | 5138 | 5218 | 15292 | 1.9671 | 2.9763 |  |  |  | Productivity (Prod) | 17 | LOC/hr
[12 empty] | Planned effort (Ep) | 2883 | Minutes
[6 empty] | min = | 0.77582 |  |  |  |  | Lower prediction interval (LPI) | 1670 | Minutes
[6 empty] | max = | 4.3742 |  |  |  |  | Upper prediction interval (UPI) | 4175 | Minutes
[12 empty] | Confidence | HIGH
[9 empty] | Construction Phase = 50% for Time In to Date so: Ep * 0.5 |  |  | How much overall effort do you anticipate expending in construction? | 1441.6213 | Minutes

## Calc-5
Supporting Calculations for
Top-down effort calculations
| Very Low | Low | Nominal | High | Very High | Extra High
Scale Factors
Precedent | 6.2 | 4.96 | 3.72 | 2.48 | 1.24 | 0 | PM Nominal
Flexibility | 5.07 | 4.05 | 3.04 | 2.03 | 1.01 | 0 | A = | 2.94
Risk resolution | 7.07 | 5.65 | 4.24 | 2.83 | 1.41 | 0 | B = | 0.91 | Person months, if all factors are nominal: | 2.41 | Person Months
Team Cohesion | 5.48 | 4.38 | 3.29 | 2.19 | 1.1 | 0 | Size = | 0.835 | Person months, worst case: | 7.52 | Person Months
Process Level | 7.8 | 6.24 | 4.68 | 3.12 | 1.56 | 0 | SUM(SF) = | 18.97 | Person months, best case: | 2.06 | Person Months
[7 empty] | PRODUCT(EM) = | 1
Cost Drivers
Product attributes | [6 empty] | PM = | 2.4112
Required software reliability | 0.82 | 0.92 | 1 | 1.1 | 1.26 | 1.26
Size of application database | 0.94 | 0.94 | 1 | 1.08 | 1.16 | 1.16
Complexity of the product | 0.7 | 0.85 | 1 | 1.15 | 1.3 | 1.65 | PM Worst
Hardware attributes | [6 empty] | A = | 2.94
Run-time performance constraints | 1 | 1 | 1 | 1.11 | 1.3 | 1.66 | B = | 0.91
Memory constraints | 1 | 1 | 1 | 1.06 | 1.21 | 1.56 | Size = | 0.835
Volatility of the virtual machine environment | 0.87 | 0.87 | 1 | 1.15 | 1.3 | 1.3 | SUM(SF) = | 31.62
Required turnabout time | 0.87 | 0.87 | 1 | 1.07 | 1.15 | 1.15 | PRODUCT(EM) = | 3.1905
Personnel attributes
Analyst capability | 1.42 | 1.19 | 1 | 0.85 | 0.71 | 0.71 | PM = | 7.5193
Applications experience | 1.22 | 1.1 | 1 | 0.88 | 0.81 | 0.81
Software engineer capability | 1.34 | 1.15 | 1 | 0.88 | 0.76 | 0.76
Virtual machine experience | 1.21 | 1.1 | 1 | 0.9 | 0.9 | 0.9 | PM Best
Programming language experience | 1.14 | 1.07 | 1 | 0.95 | 0.95 | 0.95 | A = | 2.94
Personnel continuity | 1.29 | 1.1 | 1 | 0.88 | 0.81 | 0.81 | B = | 0.91
Project attributes | [6 empty] | Size = | 0.835
Application of software engineering methods | 1.24 | 1.1 | 1 | 0.91 | 0.82 | 0.82 | SUM(SF) = | 12.65
Use of software tools | 1.24 | 1.1 | 1 | 0.91 | 0.83 | 0.83 | PRODUCT(EM) = | 0.84367
Required development schedule | 1.23 | 1.08 | 1 | 1.04 | 1.1 | 1.1
[7 empty] | PM = | 2.0575